## Sheet1
OPCD - Fair Hydro Ac |  |  |  | high priority
Risk and Issue Log |  |  |  | medium priority
low priority
ID# | Request | Purpose | Date raised | Expected output | Timeline to complete | Date of update | Date closed | Comments (Additional information)
1 | Provide comments on IESO memo re: RRA accounting | Strengthen position/identify risks wrt RRA accounting | 2019-04-01 | Comments on IESO memo | Comments sent Thursday April 20 |  |  | If IESO doesn't accomplish RRA accounting, underfunding will represent losses and gains to be recognized upon sale of recoverable). Strong case required for reflecting RRA on CFS (consistent accounting as IESO accounting on line by line consolidation basis)
2 | Document identified possible indicators of control from various legal documents | Identify indicators for and against control by OPG/other entity | 2019-04-01 | List of identified control indicators and possible impact |  |  |  | include discussion with OPG EY team; considerations include: guarantees including market disruption guarantee (i.e. commercial paper placed before bond deal - Province step in or immediately have it become due and payable), termination clause,kick out rights, other entities involved in transaction (OEB control); what happens if OPG can't buy the RRA asset? To reach out to OPG EY team to id potential issues (timing impt), e.g. termination clause. (consider - ability to replace FSM, OEB role in setting rates, termination provisions)
3 | Read various legal documents | General comments or issues related to document | 2021-04-01 | Comments on document |  |  |  | Comments on consultation v3 sent April 22 (EY to comment on impact if revenue considered a tax) (many details outstanding -- Principles, Regulations, FSM replacement if FP not aligned with principles)
4 | Consider structure of OPG Trust as SPE under OPG getting picked up by Province under modified equity and research other examples | Identify other examples of organizations consolidating through a GBE that would not be considered GBEs themselves | 2019-04-01 | Discussion/notes |  |  |  | OPG EY said termination clause OK, as long as does not impact amounts already outstanding.
5 | Map out entries at consolidated level under scenario where IESO is not permitted to record an RRA | Understand possible impact on public accounts | 2019-04-01 | Journal entries and possible impact |  |  |  | for example, consider PS3070.08 and PS3420 - interorganizational gains on assets remaining in consol entity are eliminated (reduction in investment in GBE?)
6 | Understand the transition of asset from RRA in IESO to Intangible in OPG | Identify possible risk with respect to the RRA accounting from these transactions (i.e. because OPG accounts as intangible asset - include in discussions with OPG team); also consider accounting at the provincial level for these transfers | 2019-04-01 | Discussion/notes |  |  |  | - current acctg is that it does not meet criteria of financial asset for OPG because buying from a ratepayer class and not an RRA because no costs incurred by Trust which leaves intangible but this then becomes an issue for the financing costs - also, how will they derecognize
7 | Document flow of interest and existence of related RRA and subsequent transfer to intangible asset and related impact from interest perspective | Strengthen position/identify risks wrt accounting | 2019-04-01 | Discussion/notes
8 | Consider impact of clean energy charge being deemed an unconstituational tax | Determine possible accounting impact on public accounts | 2019-04-01 | Discussion/notes |  |  |  | EY to consider
9 | Reach out to global network for examples of other PS entities following RRA (following standards other than US GAAP and IFRS) NPP advised not to raise among other firms. | Support posifor RRA in public sector financial statements | 2019-04-01 | Discussion/notes | in progress | sent email April 17 | No examples identified to-date
10 | Consider accounting if in, say 5 years, new legislation comes along that wipes out the structure | Impact to the public accounts | 2019-04-01 | Discussion/notes
Whitepapers - to address key accounting elements, what if scenarios (e.g. if FSM replaced, if guarantee exercised); Suzy advised that she will be away for a week starting on Thursday Apr. 27; E&Y to provide draft list of whitepapers to address various issues and send to OPCD for further consideration the working paper structure, points to consider)