## Colour Calendar
SEPTEMBER 2013
Sunday |  | Monday |  | Tuesday | Wednesday |  | Thursday | Friday |  | Saturday
2013-09-01 |  | 2013-09-02 | Labour Day | 2013-09-03 | 2013-09-04 |  | 2013-09-05 | 2013-09-06 |  | 2013-09-07
Last updated: |  |  |  | Burlington - Consults (DM) | Directors' Brainstorm (9-12) |  |  | Directors' Brainstorm (9-12)
Sep 15 at 12:10 PM | [7 empty] | CAB Deck to ADMs
MO - PO Deck (3-4:30)
[5 empty] | DM - Themes / Outcomes / |  | DM - Demand | DM - Conservation (RE)
[5 empty] | Pricing (RA+E) |  | Forecast (OPA+E+RE) | DM - Nuclear (E)
2013-09-08 |  | 2013-09-09 | House Resumes | 2013-09-10 | 2013-09-11 |  | 2013-09-12 | 2013-09-13 |  | 2013-09-14
|  | En Route to Kenora |  | SSM - Consults (ADM) | DM - Renewables incl. Tx |  | Whitby - Consults (DM) | Ottawa - Engagement
|  |  |  | Kenora - Consults (DM) | Considerations (RE+E) |  |  | MO - Demand Forecast (8-9:30)
[5 empty] | En Route to Toronto |  | CAB Deck to DMO | MO - Conservation (3:30-5)
DM - Tx + N of Dryden (E)
DM - Innovation + Storage (E)
2013-09-15 |  | 2013-09-16 |  | 2013-09-17 | 2013-09-18 |  | 2013-09-19 | 2013-09-20 |  | 2013-09-21
|  | Cabinet Deck to DM (noon) + MO |  | MO - Nuclear (10-12) | MO - Thermal + CHP (4:15-5) |  | DM - Renewables Round 2 (12:30-1:30) | Binder of Decks to DM + MO
|  | MO - Cabinet Deck (1-1:30) |  | DM - Clean Import (12-1) | MO - Aboriginal (6-7) |  | DM - Conservation Round 2 (1:30-2:30) | - Demand
|  | MO - Tx + N of Dryden (1:30-2:15) |  | M. Brief - Cabinet Update (3-5) |  |  | M. Approved Cabinet Deck Due | - Conservation
|  | MO - Innovation+ Storage (2:15-3) | [5 empty] | - Nuclear
|  | DM - Thermal + CHP (4-5) | [5 empty] | - Renewables
|  | MO - Renewables (5:30-6:30) | [5 empty] | - Tx + N. of Dryden
|  | DM - Aboriginal(6:30-7:30) | [5 empty] | - Innovation + Storage
- Thermal + CHP
- Aboriginal
|  | EBR posting closes | [5 empty] | - Clean Imports
EBR Summary List + Top 10 to DMO
2013-09-22 |  | 2013-09-23 |  | 2013-09-24 | 2013-09-25 |  | 2013-09-26 | 2013-09-27 |  | 2013-09-28
|  | MO - Clean Import (11-11:30) |  | DM - Sector Efficiences (11-12) | CABINET UPDATE (12-2:30) |  | Innovation Session (DM)
|  | DM - Nuclear (5-5:45) |  | DM - Oil + Gas (12-1) | Innovation Dinner (DM+M) |  | M. Brief - Demand (1:30-2)
|  |  |  | MO also available 3-6 |  |  | M. Brief - Conservation (2-2:30)
M. Brief - Nuclear (2:35-3:30)
M. Brief - Renewables (3:35-4:05)
|  | LTEP Doc - Conservation Section |  |  | LTEP Doc - Conservation Section to MO |  | M. Brief - NW Transmissions (4:05-4:30)
M. Brief - Smart Grid (5:15-5:45)
|  | to DM |  |  |  |  | M. Brief - Natural Gas Generation (5:45-6:15)
LTEP DRAFT CALENDAR - APRIL 2017
1899-12-31
1900-01-01 |  | 1900-01-02 |  | 1900-01-03 | 1900-01-04 |  | 1900-01-05 | 1900-01-06 |  | 1900-01-07
|  |  |  | DM, CoS LTEP Themes | Minister's LTEP Themes |  | PO Briefing LTEP | DM, CoS LTEP Themes
|  |  |  | (12-1:30pm) | (4:00-5:30pm) |  | (1:30-2:30pm) | (12:30-2:00pm)
|  |  |  | Indigenous, accessibility | Regional planning, maximizing assets |  |  | Climate change, supply and
[5 empty] | (electricity and fuels) |  |  | demand, innovation
1900-01-08 |  | 1900-01-09 |  | 1900-01-10 | 1900-01-11 |  | 1900-01-12 | 1900-01-13 |  | 1900-01-14
|  |  |  | DM, CoS LTEP Themes |  |  | Minister's LTEP Themes
|  |  |  | (12-1:30pm) |  |  | (6-7pm)
|  |  |  | TBD |  |  | Market-based outcomes, conservation
1900-01-15 |  | 17 |  | 18 | 19 |  | 20 | 21 |  | 1900-01-21
1900-01-22 |  | 24 |  | 25 | 26 |  | 27 | 28 |  | 1900-01-28
Minister's LTEP Themes
(5:15-6:45pm)
Accessibility, innovation, Indigenous
1900-01-29
LTEP DRAFT CALENDAR - MAY 2017
|  | 1899-12-31 |  | 1900-01-01 | 1900-01-02 |  | 1900-01-03 | 1900-01-04 |  | 1900-01-05
|  | Minister's LTEP Themes |  |  |  |  | Minister's LTEP Themes
|  | (4:30-6pm) |  |  |  |  | (3-5pm)
|  | Climate Change, supply and demand |  |  |  |  | TBD
1900-01-06 |  | 1900-01-07 |  | 1900-01-08 | 1900-01-09 |  | 1900-01-10 | 1900-01-11 |  | 1900-01-12
1900-01-13 |  | 1900-01-14 |  | 1900-01-15 | 1900-01-16 |  | 1900-01-17 | 1900-01-18 |  | 1900-01-19
1900-01-20 |  | 22 |  | 23 | 24 |  | 25 | 26 |  | 1900-01-26
1900-01-27 |  | 29 |  | 30 | 31
LTEP DRAFT CALENDAR - JUNE 2017
[7 empty] | 1899-12-31 | 1900-01-01 |  | 1900-01-02
1900-01-03 |  | 1900-01-04 |  | 1900-01-05 | 1900-01-06 |  | 1900-01-07 | 1900-01-08 |  | 1900-01-09
1900-01-10 |  | 1900-01-11 |  | 1900-01-12 | 1900-01-13 |  | 1900-01-14 | 1900-01-15 |  | 1900-01-16
1900-01-17 |  | 19 |  | 20 | 21 |  | 22 | 23 |  | 1900-01-23
1900-01-24 |  | 26 |  | 27 | 28 |  | 29 | 30
Notes:
Blue = | Deputy Briefings |  | Purple = | DM, CoS Briefings | Pink = | LTEP Document Related
Orange = | Minister's Briefings |  | Green = | Cabinet Related |  |  |  |  | V10 - Last Updated April 4, 5pm
Yellow = | Other Meetings
Cabinet / Sign-Off
Draft 4
LTEP Release
Production
Production
Draft 3
Draft 2
Draft 1
Production

## Sheet1 (hidden)
Tasks | Start Date | Duration (Days) | End Date
Themed Briefings | 2017-03-06 | 34 | 2017-04-09
LTEP Document Drafting | 2017-04-09 | 42 | 2017-05-21
Cabinet Approvals | 2017-05-15 | 6 | 2017-05-21
Formal Sign-Off | 2017-05-21 | 5 | 2017-05-26
Production and Communications Development | 2017-05-27 | 13 | 2017-06-09
Document Release and Technical Briefing | 2017-06-10 | 6 | 2017-06-16

## LTEP Products Tracking
DM/CoS Briefings
| Due Date | Briefing Date
Climate Change | April 5, EOD | 2017-04-07
Supply and Demand | April 5, EOD | 2017-04-07
Minister's Briefings
| Due Date | Briefing Date
Market-Based Outcomes | April 5, EOD | 2017-04-13
Indigenous Capacity and Leadership | April 5, EOD | 2017-04-13
Conservation | April 18, EOD | 2017-04-24
Energy Accessibility | April 18, EOD | 2017-04-24
Innovation | April 18, EOD | 2017-04-24
Climate Change | April 25, EOD | 2017-05-01
Supply and Demand | April 25, EOD | 2017-05-01