## ESP
[11 empty] | Requester Options | Holding Pen Options | Next Meeting Options | Status Options
[10 empty] | with staff | DM | with staff | DM Meeting | On Track
[10 empty] | with ADM | MO | with DMO | DM / CoS | Risk of Delay
[10 empty] | with DMO | CoS | with MO | Agency | Overdue
[10 empty] | with MO | CO/PO | with agency / other ministry | Minister
[10 empty] | Complete | Minister | complete | Cab. Committee
[11 empty] | Other Ministry |  | Stakeholder
[11 empty] | Other |  | Multicorners
Other
TBD
N/A
Deliverables Tracker - Energy Supply Policy Division
| LTEP Related | Minister's Briefings/Requests |  |  | Legislative Committee
| Item | Requester | Assigned Date | Due Date | Status | Holding the Pen | Comments / Other Details | Next Meeting | Meeting Date
| MN for minister's meeting with MOECC | Minister | 2017-04-20 | 2017-04-21 | On Track | with staff | All divisions working on MN according to confirmed agenda items | Minister | 2017-04-25
| Rate Migitation |  |  |  | Risk of Delay |  | Work is ongoing and Director of Operations leads coordination in DMO; ESP advisor happy to assist |  | 2017-04-25
| CCAP Update deck for minister's briefing | Minister | 2017-04-19 | 2017-04-21 | On Track | with staff | ESP will consolidate input from all disivions (for same meeting as above) | Minister | 2017-04-25
| Memo to LRC Chair (Min. Murray) on question about modelling GHG impacts of adding greenhouses to ICI | CO/PO |  |  | On Track | with staff | Requested as soon as convenient; FHP takes priority | N/A
| Revisions to deck discussing impact of cap and trade on transportation fuels prices | MO | 2017-01-27 |  | On Track | with staff | MO has requested the analysis, but DMO has requested the revisions - as soon as convenient
| Answer to Craig's question about power factor and ICI billing | MO | 2017-04-11 |  | On Track | with staff | Requested as soon as convenient; FHP takes priority | N/A
| ON-NL report |  | 2017-04-11 |  | On Track | with staff | Staff to incorporate Craig's (minor) edits and notify DMO if there are any pertinent next steps | N/A
| RNG deck | [5 empty] | Pending further progress with MOECC on a regulatory approach; timing TBD | N/A
| Review of PNERP materials | Other Ministry |  |  |  |  | Waiting on MCSCS to give us proposed package to post on EBR; latest check-in with MCSCS says they're targeting early May | N/A
| OPG deck for minister's briefing on OPG DGR | Other |  |  | On Track | with agency / other ministry | OPG's deck expected to be similar to previous DM/CoS deck, and expected Tuesday, April 25 | Minister | 2017-04-26
| MN for DMs EMMC Teleconference | DM | 2017-04-21 | 2017-04-28 | On Track | with staff | EMMC = Energy and Mines Ministers Conference (which is August 13-15 in New Brunswick) | DM / CoS | 2017-05-02
| IESO's deck for DM/CoS briefing on Market Renewal | CoS | 2017-04-19 | 2017-05-01 | On Track | with agency / other ministry |  | DM / CoS | 2017-05-03
| IESO's deck for minister's briefing on ON-QC Electricity Trade | CoS | 2017-04-20 | 2017-05-01 | On Track | with agency / other ministry | Deck's content will likely depend on progress with QC during week of April 24 (Deputy Imbrogno waiting on Deputy Keating's respond to draft cover memo for intertie report) | Minister | 2017-05-04
| IESO's deck for minister's briefing on Market Renewal | CoS | 2017-04-19 | 2017-05-05 | On Track | with agency / other ministry | IESO's deck for the minister will be similar to the deck for DM/CoS market renewal briefing on May 4 and will include changes reqested at that meeting | Minister | 2017-05-08
| IESO's deck for DM/CoS briefing on Bruce Power |  |  | 2017-05-15 | On Track | with agency / other ministry | This is an annual update; it will be valuable to complete the NDA agreement between ENERGY and Bruce Power before this meeting so that the IESO can share confidential information | DM / CoS | 2017-05-19
| Bruce Power NDAs |  |  | 2017-05-08 | On Track | with staff | Waiting on Legal to send "STAR" NDA and BN; Once DMO and MO are satisfied, Legal will send to Bruce to sign first, then deputy signs | DM / CoS | 2017-05-19
| MN for DMs CES Teleconference |  |  | 2017-05-22 | On Track | with staff |  | DM Meeting | 2017-05-24
| OPG deck for DM/CoS Quarterly Darlington Update | CoS | 2017-04-10 | 2017-05-23 | On Track | with agency / other ministry | Darlington update is about Darlington refurbishment, which began October 2016 | DM / CoS | 2017-05-25
| MN and/or other products for meeting with QC Energy Minsiter Arcand | CoS |  |  |  |  | May 30 meeting is still TBC; details about content and logistics still pending - therefore ESP advisor will request product when information is available; next related meeting Minister's briefing on ON-QC trade on May 4 | Minister
| Deck for CO on OPG's DGR | CO/PO | 2017-04-24 |  | On Track | with agency / other ministry | Meeting date TBD, but Keley warned Catriona King at OPG of incoming meeting (and deck request is implied)
|  | Requested By | Assigned Date | Due Date |  | Status | Status |  | Assigned Date