## ESP
[11 empty] | Requester Options | Holding Pen Options | Next Meeting Options | Status Options
[10 empty] | with staff | DM | with staff | DM Meeting | On Track
[10 empty] | with ADM | MO | with DMO | DM / CoS | Risk of Delay
[10 empty] | with DMO | CoS | with MO | Agency | Overdue
[10 empty] | with MO | CO/PO | with agency / other ministry | Minister
[10 empty] | Complete | Minister | complete | Cab. Committee
[11 empty] | Other Ministry |  | Stakeholder
[11 empty] | Other |  | Multicorners
Other
TBD
N/A
Deliverables Tracker - Energy Supply Policy Division
| LTEP Related | Minister's Briefings/Requests |  |  | Legislative Committee
| Item | Requester | Assigned Date | Due Date | Status | Holding the Pen | Comments / Other Details | Next Meeting | Meeting Date
| Rate Migitation |  |  |  | Risk of Delay |  | Work is ongoing and Director of Operations leads coordination in DMO; ESP advisor happy to assist |  | 2017-04-25
| Nuclear tech MN for PA Bob Delaney | MO | 2017-04-27 | 2017-04-28 | On Track | with staff | This will come Friday night or Saturday - the PA meets with a nuclear company on Monday, May 1 | N/A
| BN on NEB Modernizaton for CO | CO/PO | 2017-04-24 | 2017-04-28 | On Track | with staff | Keley requested after DM's talk with DM Betzner; expected Friday night | N/A
| BN on how to maintain CES for CO | CO/PO | 2017-04-24 | 2017-04-28 | Risk of Delay | with staff | Keley requested after DM's talk with DM Betzner; ADMO has reviewed once and requested revisions; ESP flagged it'll come early next week - Eric concurs this is appropriate | N/A
| Feedback to NRCan on their draft list of stakeholder invitations for EMMC 2017 | Other | 2017-04-27 |  | Risk of Delay | with staff | ESP to let NRCan know they won't meet short turnaround request (for April 28), and sending comments to DMO for review asap | N/A
| IESO's deck for DM/CoS briefing on Market Renewal: LMP | CoS | 2017-04-19 | 2017-05-03 | On Track | with agency / other ministry |  | DM / CoS | 2017-05-08
| OPG deck for SoC briefing on OPG's DGR | CO/PO | 2017-04-24 | 2017-05-04 | On Track | with agency / other ministry | OPG's deck expected to be very similar to Minister's deck from April 26 | Multicorners | 2017-05-05
| IESO's deck for minister's briefing on ON-QC Electricity Trade | CoS | 2017-04-20 |  | On Track | with agency / other ministry | This minister's briefing is scheduled for May 4, but both CoS and IESO CEO have expressed interest in rescheduling, which will be resolved in the next few days | Minister | 2017-05-04
| IESO's deck for minister's briefing on Market Renewal | CoS | 2017-04-19 |  | On Track | with agency / other ministry | This minister's briefing is scheduled for May 8, but both CoS and IESO CEO have expressed interest in rescheduling, which will be resolved in the next few days | Minister | 2017-05-08
| Response letter to Muriel Chudiak re: carbon cost in OEB delivery line | CoS | 2017-04-28 | 2017-05-05 | On Track | with staff | Addressed to Andrew Bevan; Muriel may have the ear of the premier? | N/A
| Response letter to AMCPO's April 20 letter | MO | 2017-04-25 | 2017-05-05 | On Track | with staff | Alexa requested on Eric's behalf on April 25 | N/A
| Bruce Power NDAs |  |  | 2017-05-08 | On Track | with MO | Craig has expressed comfort - waiting to see if Andrew chimes in. Once MO is satisfied, Legal will send to Bruce to sign first, then minister signs | DM / CoS | 2017-05-19
| IESO's deck for DM/CoS briefing on Bruce Power |  |  | 2017-05-15 | On Track | with agency / other ministry | This is an annual update; it will be valuable to complete the NDA agreement between ENERGY and Bruce Power before this meeting so that the IESO can share confidential information | DM / CoS | 2017-05-19
| MN for DMs May 18 EMMC Teleconference | DM | 2017-04-21 | 2017-05-16 | On Track | with staff | Two FYIs: 1) EMMC = Energy and Mines Ministers Conference (which is August 13-15 in New Brunswick); and 2) NRCan often posts agenda and supporting materials for calls very late, hence the May 16 deadline | DM / CoS | 2017-05-18
| Review of PNERP materials | Other Ministry |  |  |  |  | Waiting on MCSCS to give us proposed package to post on EBR; latest check-in with MCSCS says they're targeting early May | N/A
| MN for DMs CES Teleconference |  |  | 2017-05-22 | On Track | with staff |  | DM Meeting | 2017-05-24
| OPG deck for DM/CoS Quarterly Darlington Update | CoS | 2017-04-10 | 2017-05-23 | On Track | with agency / other ministry | Darlington update is about Darlington refurbishment, which began October 2016 | DM / CoS | 2017-05-25
| Revisions to deck discussing impact of cap and trade on transportation fuels prices | MO | 2017-01-27 |  | On Track | with staff | MO has requested the analysis, but DMO has requested the revisions - as soon as convenient | N/A
| ON-NL report |  | 2017-04-11 |  | On Track | with staff | Staff to incorporate Craig's (minor) edits and notify DMO if there are any pertinent next steps | N/A
| Memo to LRC Chair (Min. Murray) on question about modelling GHG impacts of adding greenhouses to ICI | CO/PO |  |  | On Track | with staff | Requested as soon as convenient; FHP takes priority | N/A
| RNG deck | [5 empty] | Pending further progress with MOECC on a regulatory approach; timing TBD | N/A
| MN and/or other products for meeting with QC Energy Minsiter Arcand | CoS |  |  |  |  | May 30 meeting is still TBC; details about content and logistics still pending - therefore ESP advisor will request product when information is available; next related meeting Minister's briefing on ON-QC trade on May 4 | Minister | 2017-05-30
|  | Requested By | Assigned Date | Due Date |  | Status | Status |  | Assigned Date