## ESP
[11 empty] | Requester Options | Holding Pen Options | Next Meeting Options | Status Options
[10 empty] | with staff | DM | with staff | DM Meeting | On Track
[10 empty] | with ADM | MO | with DMO | DM / CoS | Risk of Delay
[10 empty] | with DMO | CoS | with MO | Agency | Overdue
[10 empty] | with MO | CO/PO | with agency / other ministry | Minister
[10 empty] | Complete | Minister | complete | Cab. Committee
[11 empty] | Other Ministry |  | Stakeholder
[11 empty] | Other |  | Multicorners
Other
TBD
N/A
Deliverables Tracker - Energy Supply Policy Division
| LTEP Related | Minister's Briefings/Requests |  |  | Legislative Committee
| Item | Requester | Assigned Date | Due Date | Status | Holding the Pen | Comments / Other Details | Next Meeting | Meeting Date
| Rate Migitation |  |  |  | Risk of Delay |  | Work is ongoing and Director of Operations leads coordination in DMO; ESP advisor happy to assist | DM / CoS | 2017-05-08
| BN on NEB Modernizaton for CO | CO/PO | 2017-04-24 |  | Risk of Delay | with staff | This is with Steen - FHP is priority; original request was for May 28 | N/A
| BN on how to maintain CES for CO | CO/PO | 2017-04-24 |  | Risk of Delay | with staff | ADM has reviewed and requested changes; original request was for May 28 | N/A
| Deck on DGR for CoS to brief PO/CO | CoS | 2017-05-01 | 2017-05-05 | Risk of Delay | with staff | Deck is well underway, but may not arrive on May 5 | N/A
| Questions for Craig on white paper about MEDG indstrial funding | MO | 2017-05-01 |  |  | with staff |  | DM / CoS | 2017-05-16
| IESO's deck for minister's briefing on ON-QC Electricity Trade | CoS | 2017-04-20 | 2017-05-10 | On Track | with agency / other ministry | CoS would like the deck by May 12; Minister's briefing is on May 18 | Minister | 2017-05-18
| IESO's deck for minister's briefing on Market Renewal | CoS | 2017-04-19 |  | On Track | with agency / other ministry | Guidance for this deck to be determined after the May 8 DM/CoS market renewal briefing | Minister | 2017-05-18
| Response letter to Muriel Chudiak re: carbon cost in OEB delivery line | CoS | 2017-04-28 | 2017-05-05 | On Track | with staff | Addressed to Andrew Bevan; Muriel may have the ear of the premier? | N/A
| Response letter to AMCPO's April 20 letter | MO | 2017-04-25 | 2017-05-08 | On Track | with staff | Revisions requested May 5 | N/A
| Bruce Power NDAs |  |  | 2017-05-10 | On Track | with staff | Legal has sent to Bruce Power for signing and expresses confidence with completing before the May 19 IESO briefing on Bruce Power | DM / CoS | 2017-05-19
| IESO's deck for DM/CoS briefing on Bruce Power |  |  | 2017-05-15 | On Track | with agency / other ministry | This is an annual update; it will be valuable to complete the NDA agreement between ENERGY and Bruce Power before this meeting so that the IESO can share confidential information | DM / CoS | 2017-05-19
| MN for DMs May 18 EMMC Teleconference | DM | 2017-04-21 | 2017-05-16 | On Track | with staff | Two FYIs: 1) EMMC = Energy and Mines Ministers Conference (which is August 13-15 in New Brunswick); and 2) NRCan often posts agenda and supporting materials for calls very late, hence the May 16 deadline | DM / CoS | 2017-05-18
| Review of PNERP materials | Other Ministry |  |  |  |  | Waiting on MCSCS to give us proposed package to post on EBR; latest check-in with MCSCS says they're targeting early May | N/A
| MN for DMs CES Teleconference |  |  | 2017-05-22 | On Track | with staff |  | DM Meeting | 2017-05-24
| OPG deck for DM/CoS Quarterly Darlington Update | CoS | 2017-04-10 | 2017-05-23 | On Track | with agency / other ministry | Darlington update is about Darlington refurbishment, which began October 2016 | DM / CoS | 2017-05-25
| Revisions to deck discussing impact of cap and trade on transportation fuels prices | MO | 2017-01-27 |  | On Track | with staff | MO has requested the analysis, but DMO has requested the revisions - as soon as convenient | N/A
| ON-NL report |  | 2017-04-11 |  | On Track | with staff | Staff to incorporate Craig's (minor) edits and notify DMO if there are any pertinent next steps | N/A
| Memo to LRC Chair (Min. Murray) on question about modelling GHG impacts of adding greenhouses to ICI | CO/PO |  |  | On Track | with staff | Requested as soon as convenient; FHP takes priority | N/A
| RNG deck | [5 empty] | Pending further progress with MOECC on a regulatory approach; timing TBD | N/A
| MN and/or other products for meeting with QC Energy Minsiter Arcand | CoS | 2017-05-05 | 2017-05-22 | On Track | with staff | Dinner tentatively May 29 and meeting May 30, but details still TBC - I checked with MO on May 5 | Minister | 2017-05-30
|  | Requested By | Assigned Date | Due Date |  | Status | Status |  | Assigned Date