## Colour Calendar
SEPTEMBER 2013
Sunday |  | Monday |  | Tuesday | Wednesday |  | Thursday | Friday |  | Saturday
2013-09-01 |  | 2013-09-02 | Labour Day | 2013-09-03 | 2013-09-04 |  | 2013-09-05 | 2013-09-06 |  | 2013-09-07
Last updated: |  |  |  | Burlington - Consults (DM) | Directors' Brainstorm (9-12) |  |  | Directors' Brainstorm (9-12)
Sep 15 at 12:10 PM | [7 empty] | CAB Deck to ADMs
MO - PO Deck (3-4:30)
[5 empty] | DM - Themes / Outcomes / |  | DM - Demand | DM - Conservation (RE)
[5 empty] | Pricing (RA+E) |  | Forecast (OPA+E+RE) | DM - Nuclear (E)
2013-09-08 |  | 2013-09-09 | House Resumes | 2013-09-10 | 2013-09-11 |  | 2013-09-12 | 2013-09-13 |  | 2013-09-14
|  | En Route to Kenora |  | SSM - Consults (ADM) | DM - Renewables incl. Tx |  | Whitby - Consults (DM) | Ottawa - Engagement
|  |  |  | Kenora - Consults (DM) | Considerations (RE+E) |  |  | MO - Demand Forecast (8-9:30)
[5 empty] | En Route to Toronto |  | CAB Deck to DMO | MO - Conservation (3:30-5)
DM - Tx + N of Dryden (E)
DM - Innovation + Storage (E)
2013-09-15 |  | 2013-09-16 |  | 2013-09-17 | 2013-09-18 |  | 2013-09-19 | 2013-09-20 |  | 2013-09-21
|  | Cabinet Deck to DM (noon) + MO |  | MO - Nuclear (10-12) | MO - Thermal + CHP (4:15-5) |  | DM - Renewables Round 2 (12:30-1:30) | Binder of Decks to DM + MO
|  | MO - Cabinet Deck (1-1:30) |  | DM - Clean Import (12-1) | MO - Aboriginal (6-7) |  | DM - Conservation Round 2 (1:30-2:30) | - Demand
|  | MO - Tx + N of Dryden (1:30-2:15) |  | M. Brief - Cabinet Update (3-5) |  |  | M. Approved Cabinet Deck Due | - Conservation
|  | MO - Innovation+ Storage (2:15-3) | [5 empty] | - Nuclear
|  | DM - Thermal + CHP (4-5) | [5 empty] | - Renewables
|  | MO - Renewables (5:30-6:30) | [5 empty] | - Tx + N. of Dryden
|  | DM - Aboriginal(6:30-7:30) | [5 empty] | - Innovation + Storage
- Thermal + CHP
- Aboriginal
|  | EBR posting closes | [5 empty] | - Clean Imports
EBR Summary List + Top 10 to DMO
2013-09-22 |  | 2013-09-23 |  | 2013-09-24 | 2013-09-25 |  | 2013-09-26 | 2013-09-27 |  | 2013-09-28
|  | MO - Clean Import (11-11:30) |  | DM - Sector Efficiences (11-12) | CABINET UPDATE (12-2:30) |  | Innovation Session (DM)
|  | DM - Nuclear (5-5:45) |  | DM - Oil + Gas (12-1) | Innovation Dinner (DM+M) |  | M. Brief - Demand (1:30-2)
|  |  |  | MO also available 3-6 |  |  | M. Brief - Conservation (2-2:30)
M. Brief - Nuclear (2:35-3:30)
M. Brief - Renewables (3:35-4:05)
|  | LTEP Doc - Conservation Section |  |  | LTEP Doc - Conservation Section to MO |  | M. Brief - NW Transmissions (4:05-4:30)
M. Brief - Smart Grid (5:15-5:45)
|  | to DM |  |  |  |  | M. Brief - Natural Gas Generation (5:45-6:15)
LTEP DRAFT CALENDAR - MAY 2017
|  | 1899-12-31 |  | 1900-01-01 | 1900-01-02 |  | 1900-01-03 | 1900-01-04 |  | 1900-01-05
DM, CoS, OEB LTEP Themes
(3-4pm)
Energy Accessibility
DM, CoS LTEP Themes
(4-5pm)
Directions, ToC, Minsiter's Message
1900-01-06 |  | 1900-01-07 |  | 1900-01-08 | 1900-01-09 |  | 1900-01-10 | 1900-01-11 |  | 1900-01-12
|  | Minister's LTEP Themes |  |  |  |  | PA Briefing LTEP Nuclear
|  | (2-3pm) |  |  |  |  | (3-3:45pm)
Conservation
1900-01-13 |  | 1900-01-14 |  | 1900-01-15 | 1900-01-16 |  | 1900-01-17 | 1900-01-18 |  | 1900-01-19
[5 empty] | PO Briefing LTEP |  | DM, CoS LTEP Themes | DM Meeting OEB Decks
[5 empty] | (11am-12pm) |  | (3-4pm) | (3-3:45pm)
[5 empty] | Fuels |  | Update
[5 empty] | Minister's LTEP Themes |  | PA Briefing LTEP Fuels
[5 empty] | (8-9am) |  | (1:30-2:15pm)
Climate Change
1900-01-20 |  | 22 |  | 23 | 24 |  | 25 | 26 |  | 1900-01-26
|  |  |  | PO Briefing LTEP | DM, CoS LTEP Themes
|  |  |  | TBD This week | (4:30-5:30pm)
|  |  |  | To be cancelled | Modeling
1900-01-27 |  | 29 |  | 30 | 31
|  | Minister's LTEP Themes |  |  | PO Briefing LTEP
|  | (12:30-2pm) |  |  | (11am-12pm)
|  | Energy Accessibility and Innovation |  |  | Conservation
LTEP DRAFT CALENDAR - JUNE 2017
[7 empty] | 1899-12-31 | 1900-01-01 |  | 1900-01-02
1900-01-03 |  | 1900-01-04 |  | 1900-01-05 | 1900-01-06 |  | 1900-01-07 | 1900-01-08 |  | 1900-01-09
DM, CoS LTEP Themes
(1:30-3pm)
Directions
1900-01-10 |  | 1900-01-11 |  | 1900-01-12 | 1900-01-13 |  | 1900-01-14 | 1900-01-15 |  | 1900-01-16
PO Briefing LTEP
TBD This week
Innovation and Customer Choice
1900-01-17 |  | 19 |  | 20 | 21 |  | 22 | 23 |  | 1900-01-23
1900-01-24 |  | 26 |  | 27 | 28 |  | 29 | 30
PO Briefing LTEP
TBD This week
Supply and Demand
LTEP DRAFT CALENDAR - July 2017
1
1900-01-01 |  | 1900-01-02 |  | 1900-01-03 | 1900-01-04 |  | 1900-01-05 | 1900-01-06 |  | 1900-01-07
1900-01-08 |  | 1900-01-09 |  | 1900-01-10 | 1900-01-11 |  | 1900-01-12 | 1900-01-13 |  | 1900-01-14
PO Briefing LTEP
TBD This week
Draft Cabinet Submission
1900-01-15 |  | 17 |  | 18 | 19 |  | 20 | 21 |  | 1900-01-21
1900-01-22 |  | 24 |  | 25 | 26 |  | 27 | 28 |  | 1900-01-28
|  | PO Briefing LTEP |  |  | Cabinet (Special)
TBD This week
Final Cabinet Submission
1900-01-29 |  | 31
Blue = | Deputy Briefings |  | Purple = | DM, CoS Briefings | Pink = | LTEP Document Related
Orange = | Minister's Briefings |  | Green = | Cabinet Related |  |  |  |  | V19 - Last Updated May 16, 10am
Yellow = | Other Meetings

## Sheet1 (hidden)
Tasks | Start Date | Duration (Days) | End Date
Themed Briefings | 2017-03-06 | 34 | 2017-04-09
LTEP Document Drafting | 2017-04-09 | 42 | 2017-05-21
Cabinet Approvals | 2017-05-15 | 6 | 2017-05-21
Formal Sign-Off | 2017-05-21 | 5 | 2017-05-26
Production and Communications Development | 2017-05-27 | 13 | 2017-06-09
Document Release and Technical Briefing | 2017-06-10 | 6 | 2017-06-16

## LTEP Products Tracking
Deputy Briefings
| Due Date | Briefing Date
Energy Accessibility / Innovation | May 17, EOD | 2017-05-19
DM/CoS Briefings
| Due Date | Briefing Date
LTEP Process Update | May 16, mid-day | 2017-05-18
IESO Modeling (provided by IESO) | May 19, EOD | 2017-05-24
Directions | June 5, EOD | 2017-06-08
Minister's Briefings
| Due Date | Briefing Date
Climate Change - Complete | April 26, EOD | 2017-05-10
Energy Accessibility | May 24, EOD | 2017-05-29
Innovation | May 24, EOD | 2017-05-29
PO Briefings - Briefings from May 23 Onwards Expected to Change
| Due Date | Briefing Date
Fuels Briefing | May 8, EOD | 2017-05-17
Conservation | May 23, EOD | 2017-05-31
Innovation and Customer Choice | June 5, EOD | Week of June 12 (TBD)
Supply and Demand | June 19, EOD | Week of June 26 (TBD)
Draft Cabinet Submission | July 4, EOD | Week of July 10 (TBD)
Final Cabinet Submission | July 17, EOD | Week of July 24 (TBD)