## Colour Calendar
SEPTEMBER 2013
Sunday |  | Monday |  | Tuesday | Wednesday |  | Thursday | Friday |  | Saturday
2013-09-01 |  | 2013-09-02 | Labour Day | 2013-09-03 | 2013-09-04 |  | 2013-09-05 | 2013-09-06 |  | 2013-09-07
Last updated: |  |  |  | Burlington - Consults (DM) | Directors' Brainstorm (9-12) |  |  | Directors' Brainstorm (9-12)
Sep 15 at 12:10 PM | [7 empty] | CAB Deck to ADMs
MO - PO Deck (3-4:30)
[5 empty] | DM - Themes / Outcomes / |  | DM - Demand | DM - Conservation (RE)
[5 empty] | Pricing (RA+E) |  | Forecast (OPA+E+RE) | DM - Nuclear (E)
2013-09-08 |  | 2013-09-09 | House Resumes | 2013-09-10 | 2013-09-11 |  | 2013-09-12 | 2013-09-13 |  | 2013-09-14
|  | En Route to Kenora |  | SSM - Consults (ADM) | DM - Renewables incl. Tx |  | Whitby - Consults (DM) | Ottawa - Engagement
|  |  |  | Kenora - Consults (DM) | Considerations (RE+E) |  |  | MO - Demand Forecast (8-9:30)
[5 empty] | En Route to Toronto |  | CAB Deck to DMO | MO - Conservation (3:30-5)
DM - Tx + N of Dryden (E)
DM - Innovation + Storage (E)
2013-09-15 |  | 2013-09-16 |  | 2013-09-17 | 2013-09-18 |  | 2013-09-19 | 2013-09-20 |  | 2013-09-21
|  | Cabinet Deck to DM (noon) + MO |  | MO - Nuclear (10-12) | MO - Thermal + CHP (4:15-5) |  | DM - Renewables Round 2 (12:30-1:30) | Binder of Decks to DM + MO
|  | MO - Cabinet Deck (1-1:30) |  | DM - Clean Import (12-1) | MO - Aboriginal (6-7) |  | DM - Conservation Round 2 (1:30-2:30) | - Demand
|  | MO - Tx + N of Dryden (1:30-2:15) |  | M. Brief - Cabinet Update (3-5) |  |  | M. Approved Cabinet Deck Due | - Conservation
|  | MO - Innovation+ Storage (2:15-3) | [5 empty] | - Nuclear
|  | DM - Thermal + CHP (4-5) | [5 empty] | - Renewables
|  | MO - Renewables (5:30-6:30) | [5 empty] | - Tx + N. of Dryden
|  | DM - Aboriginal(6:30-7:30) | [5 empty] | - Innovation + Storage
- Thermal + CHP
- Aboriginal
|  | EBR posting closes | [5 empty] | - Clean Imports
EBR Summary List + Top 10 to DMO
2013-09-22 |  | 2013-09-23 |  | 2013-09-24 | 2013-09-25 |  | 2013-09-26 | 2013-09-27 |  | 2013-09-28
|  | MO - Clean Import (11-11:30) |  | DM - Sector Efficiences (11-12) | CABINET UPDATE (12-2:30) |  | Innovation Session (DM)
|  | DM - Nuclear (5-5:45) |  | DM - Oil + Gas (12-1) | Innovation Dinner (DM+M) |  | M. Brief - Demand (1:30-2)
|  |  |  | MO also available 3-6 |  |  | M. Brief - Conservation (2-2:30)
M. Brief - Nuclear (2:35-3:30)
M. Brief - Renewables (3:35-4:05)
|  | LTEP Doc - Conservation Section |  |  | LTEP Doc - Conservation Section to MO |  | M. Brief - NW Transmissions (4:05-4:30)
M. Brief - Smart Grid (5:15-5:45)
|  | to DM |  |  |  |  | M. Brief - Natural Gas Generation (5:45-6:15)
LTEP DRAFT CALENDAR - JULY 2017
1
1900-01-01 |  | 1900-01-02 |  | 1900-01-03 | 1900-01-04 |  | 1900-01-05 | 1900-01-06 |  | 1900-01-07
|  |  |  | Draft from Writer for Review |  |  |  | Draft to Writer for Revision
Draft cabsub to MO
1900-01-08 |  | 1900-01-09 |  | 1900-01-10 | 1900-01-11 |  | 1900-01-12 | 1900-01-13 |  | 1900-01-14
|  | Draft from Writer for Review |  | DM, CoS LTEP Themes | PO Briefing LTEP |  | PO Briefing LTEP | Draft to Writer for Revision
|  | MO Comments Due on Cabsub |  | (9:30-11:30am) | (4-5pm) |  | (12:30-1:30pm) | Draft cabsub to MO
|  |  |  | Table read of cabsub | Draft Cabinet Submission |  | Price Curve | Draft Directions to MO
|  |  |  | Draft cabsub to MO/CO | MO Comments Due
1900-01-15 |  | 17 |  | 18 | 19 |  | 20 | 21 |  | 1900-01-21
|  | DM, CoS LTEP Cabinet Sub |  | Minister's Briefing LTEP | Minister's Briefing RNG |  | PO Briefing LTEP | Draft to Writer for Revision
|  | (9-10:30am) |  | (10:15am-11am) | (9-10am) |  | (11:50am-1:30pm)
|  | Table read of cabsub |  | Cabinet Submission | Final Directions due to CO |  | Draft Cabinet Submission
|  | Draft from Writer for Review |  | Minister's Briefing LTEP | Final cabsub to CO
|  | MO Comments Due on Cabsub |  | (11-11:45am) | MO Comments Due
Price Curve
1900-01-22 |  | 24 |  | 25 | 26 |  | 27 | 28 |  | 1900-01-28
|  | Draft from Writer for Review |  | Minister's Briefing LTEP | CABINET |  |  | Draft to Writer for Revision
|  |  |  | (8:30-10am) | LTEP Part 1 |  |  | Draft TB Submission Due
|  |  |  | TBD | MO Comments Due
1900-01-29 |  | 31
Draft from Writer for Review
LTEP DRAFT CALENDAR -AUGUST 2017
|  |  |  | 1 | 2 |  | 3 | 4 |  | 5
|  |  |  | MO comments due on TB Sub | MO Comments Due |  |  | Draft TB Submission Due
|  |  |  | DM, CoS LTEP Cabinet Sub | PO Briefing LTEP (TBD) |  |  | Draft to Writer for Revision
|  |  |  | (9-10:30am) | (1:30-2:30pm)
|  |  |  | Table read of cabsub | Price Curve
1900-01-05 |  | 1900-01-06 |  | 1900-01-07 | 1900-01-08 |  | 1900-01-09 | 1900-01-10 |  | 1900-01-11
|  |  |  | MO comments due on TB Sub | MO Comments Due |  | Finalize TB Sub | Draft to Writer for Revision
|  |  |  | Draft from Writer for Review | DM, CoS LTEP Cabinet Sub
(2-3:30pm)
Table read of cabsub
1900-01-12 |  | 1900-01-13 |  | 1900-01-14 | 1900-01-15 |  | 1900-01-16 | 1900-01-17 |  | 1900-01-18
|  | Final Review from Writer |  |  | MO Comments Due |  |  | Draft to Writer for Revision
TREASURY BOARD
SGF, IDF Approval
1900-01-19 |  | 21 |  | 22 | 23 |  | 24 | 25 |  | 1900-01-25
|  | Draft from Writer for Review |  |  | MO Comments Due |  |  | Draft to Writer for Revision
1900-01-26 |  | 28 |  | 29 | 30 |  | 31 | 1 |  | 1900-01-01
|  | Draft from Writer for Review |  |  | MO Comments Due |  | CABINET | PENS DOWN
LTEP Part 2
LTEP DRAFT CALENDAR - SEPTEMBER 2017
3 |  | 4 |  | 5 | 6 |  | 7 | 8 |  | 9
1900-01-09 |  | 1900-01-10 |  | 1900-01-11 | 1900-01-12 |  | 1900-01-13 | 1900-01-14 |  | 1900-01-15
1900-01-16 |  | 1900-01-17 |  | 1900-01-18 | 1900-01-19 |  | 1900-01-20 | 1900-01-21 |  | 1900-01-22
1900-01-23 |  | 25 |  | 26 | 27 |  | 28 | 28 |  | 1900-01-29
LTEP DRAFT CALENDAR - OCTOBER 2017
1 |  | 2 |  | 3 | 4 |  | 5 | 6 |  | 7
CABINET- Tabling
1900-01-07 |  | 1900-01-08 |  | 1900-01-09 | 1900-01-10 |  | 1900-01-11 | 1900-01-12 |  | 1900-01-13
1900-01-14 |  | 1900-01-15 |  | 1900-01-16 | 1900-01-17 |  | 1900-01-18 | 1900-01-19 |  | 1900-01-20
1900-01-21 |  | 23 |  | 24 | 25 |  | 26 | 27 |  | 1900-01-27
1900-01-28 |  | 30 |  | 31
Blue = | DM Briefings |  | Purple = | DM, CoS Briefings | Pink = | LTEP Document Related
Orange = | Min. Briefings |  | Green = | Cabinet Related |  |  |  |  | V32 Last Updated July 25, 10am
Yellow = | PO Briefings |  | Grey= | Non-LTEP Briefings
Potential LTEP Release
Layout/Translation/Print
Sign-Off
Layout/Translation/Print
Layout/Translation/Print
Layout/Translation/Print
Copy Edit

## Sheet1 (hidden)
Tasks | Start Date | Duration (Days) | End Date
Themed Briefings | 2017-03-06 | 34 | 2017-04-09
LTEP Document Drafting | 2017-04-09 | 42 | 2017-05-21
Cabinet Approvals | 2017-05-15 | 6 | 2017-05-21
Formal Sign-Off | 2017-05-21 | 5 | 2017-05-26
Production and Communications Development | 2017-05-27 | 13 | 2017-06-09
Document Release and Technical Briefing | 2017-06-10 | 6 | 2017-06-16