## Colour Calendar
SEPTEMBER 2013
Sunday |  | Monday |  | Tuesday | Wednesday |  | Thursday | Friday | Saturday
2013-09-01 |  | 2013-09-02 | Labour Day | 2013-09-03 | 2013-09-04 |  | 2013-09-05 | 2013-09-06 | 2013-09-07
Last updated: |  |  |  | Burlington - Consults (DM) | Directors' Brainstorm (9-12) |  |  | Directors' Brainstorm (9-12)
Sep 15 at 12:10 PM | [7 empty] | CAB Deck to ADMs
MO - PO Deck (3-4:30)
[5 empty] | DM - Themes / Outcomes / |  | DM - Demand | DM - Conservation (RE)
[5 empty] | Pricing (RA+E) |  | Forecast (OPA+E+RE) | DM - Nuclear (E)
2013-09-08 |  | 2013-09-09 | House Resumes | 2013-09-10 | 2013-09-11 |  | 2013-09-12 | 2013-09-13 | 2013-09-14
|  | En Route to Kenora |  | SSM - Consults (ADM) | DM - Renewables incl. Tx |  | Whitby - Consults (DM) | Ottawa - Engagement
|  |  |  | Kenora - Consults (DM) | Considerations (RE+E) |  |  | MO - Demand Forecast (8-9:30)
[5 empty] | En Route to Toronto |  | CAB Deck to DMO | MO - Conservation (3:30-5)
DM - Tx + N of Dryden (E)
DM - Innovation + Storage (E)
2013-09-15 |  | 2013-09-16 |  | 2013-09-17 | 2013-09-18 |  | 2013-09-19 | 2013-09-20 | 2013-09-21
|  | Cabinet Deck to DM (noon) + MO |  | MO - Nuclear (10-12) | MO - Thermal + CHP (4:15-5) |  | DM - Renewables Round 2 (12:30-1:30) | Binder of Decks to DM + MO
|  | MO - Cabinet Deck (1-1:30) |  | DM - Clean Import (12-1) | MO - Aboriginal (6-7) |  | DM - Conservation Round 2 (1:30-2:30) | - Demand
|  | MO - Tx + N of Dryden (1:30-2:15) |  | M. Brief - Cabinet Update (3-5) |  |  | M. Approved Cabinet Deck Due | - Conservation
|  | MO - Innovation+ Storage (2:15-3) | [5 empty] | - Nuclear
|  | DM - Thermal + CHP (4-5) | [5 empty] | - Renewables
|  | MO - Renewables (5:30-6:30) | [5 empty] | - Tx + N. of Dryden
|  | DM - Aboriginal(6:30-7:30) | [5 empty] | - Innovation + Storage
- Thermal + CHP
- Aboriginal
|  | EBR posting closes | [5 empty] | - Clean Imports
EBR Summary List + Top 10 to DMO
2013-09-22 |  | 2013-09-23 |  | 2013-09-24 | 2013-09-25 |  | 2013-09-26 | 2013-09-27 | 2013-09-28
|  | MO - Clean Import (11-11:30) |  | DM - Sector Efficiences (11-12) | CABINET UPDATE (12-2:30) |  | Innovation Session (DM)
|  | DM - Nuclear (5-5:45) |  | DM - Oil + Gas (12-1) | Innovation Dinner (DM+M) |  | M. Brief - Demand (1:30-2)
|  |  |  | MO also available 3-6 |  |  | M. Brief - Conservation (2-2:30)
M. Brief - Nuclear (2:35-3:30)
M. Brief - Renewables (3:35-4:05)
|  | LTEP Doc - Conservation Section |  |  | LTEP Doc - Conservation Section to MO |  | M. Brief - NW Transmissions (4:05-4:30)
M. Brief - Smart Grid (5:15-5:45)
|  | to DM |  |  |  |  | M. Brief - Natural Gas Generation (5:45-6:15)
|  | LTEP DRAFT CALENDAR -AUGUST 2017 | [7 empty] | LTEP DOCUMENT TRACKING
1900-01-19 |  | 21 |  | 22 | 23 |  | 24 | 25 | 1900-01-25 | 2017-08-21
|  | EBR Posting Closes |  | DM, CoS, MOECC Meeting | Ministry Edits Due |  |  | Draft to Writer for Revision |  | Monday Aug 21 | John shares revised LTEP document with Ministry
|  | Draft from Writer for Review |  | (4:30-5:30pm) | IESO Edits Due |  |  | HOLD - LTEP Document Review |  | Monday Aug 21 - Wednesday Aug 23 | Ministry, MO, IESO, review document
|  |  |  | IESO GHG LTEP Modelling | MO Edits Due |  |  | TBD |  | Wednesday Aug 23 | Ministry, MO, IESO, PO/CO provide edits
[5 empty] | PO/CO Edits Due |  |  |  |  | Thursday Aug 24 | Ministry turns all edit
[5 empty] | DM, CoS LTEP Outlooks |  |  |  |  | Friday Aug 25 | Meeting to review consolidated edits
[5 empty] | (11:15-12:45pm) | [5 empty] | Share revised draft with John McGrath end of day
[5 empty] | Cabinet Submission |  |  |  |  | Saturday Aug 26 - Sunday Aug 27 | John McGrath turns LTEP document
PO Briefing LTEP
(2-3pm)
Communications
1900-01-26 |  | 28 |  | 29 | 30 |  | 31 | 1 | 1900-01-01 | 2017-08-28
|  | Draft from Writer for Review |  | Minister's Briefing LTEP | Other Ministry Comments Due |  | CABINET | HOLD - LTEP Document Review |  | Monday Aug 28 | John shares revised LTEP document with Ministry
|  | Other Ministry Review |  | (5-6pm) |  |  | (12-3pm) | Review other Ministry Edits |  |  | Ministry identifies excerpts to share with other Ministries
|  |  |  | Cabinet Submission |  |  | LTEP Part 2, SGF, Frequency Reg | TBD |  |  | Share LTEP document with other Ministries by EOD
|  |  |  | LRC |  |  |  | Share with CO / PO |  | Tuesday Aug 29 - Wednesday Aug 30 | Other Ministries review their LTEP excerpts
|  |  |  | TBD |  |  |  | Outline and timeline for |  | Wednesday Aug 30 | Other Ministries provide edits to LTEP excerpts
|  |  |  | LTEP Frequency Regulation |  |  |  | electricity and fuels modules |  | Thursday Aug 31 | Ministry incorporates edits received from other Ministries
[10 empty] | Friday Sept 1 | Meeting to accept/reject edits from other Ministries
Share revised LTEP document with PO/CO for final review
Outline of electricity and fuels modules due
[10 empty] | Saturday Sept 2 - Sunday Sept 3 | CO/PO review LTEP document
LTEP DRAFT CALENDAR - SEPTEMBER 2017
3 |  | 4 |  | 5 | 6 |  | 7 | 8 | 9 | 2017-09-04
[5 empty] | PO Briefing LTEP |  |  | PENS DOWN |  | Tuesday Sept 5 | CO/PO review LTEP document
[5 empty] | TBD |  |  | Update on Modules |  | Wednesday Sept 6 | PO/CO provide final edits/sign-off on LTEP document
[5 empty] | LTEP Document and Comms |  |  |  |  | Friday Sept 8 | PENS DOWN
[5 empty] | CO/PO Final Sign-Off |  |  |  |  | Tuesday Sept 5 - Friday Sept | Module and technical briefing deck development
1900-01-09 |  | 1900-01-10 |  | 1900-01-11 | 1900-01-12 |  | 1900-01-13 | 1900-01-14 | 1900-01-15 | 2017-09-11
|  |  |  | Minister's Briefing LTEP |  |  |  | Update on Modules |  | Monday Sept 11 | Ministry staff sign-off on LTEP document
|  |  |  | (5:30-7pm) | [5 empty] | Tuesday Sept 13 | DM, MO, IESO sign-off on LTEP document
|  |  |  | Minister Sign-Off on LTEP document | [5 empty] | Monday Sept 11 - Tuesday Sept 12 | Copy Edit
[10 empty] | Wednesday Sept 13 - Friday Sept 15 | Layout / Translation / Print
[10 empty] | Monday Sept 11 - Friday Sept 15 | Module and technical briefing deck development
1900-01-16 |  | 1900-01-17 |  | 1900-01-18 | 1900-01-19 |  | 1900-01-20 | 1900-01-21 | 1900-01-22 | 2017-09-18
[5 empty] | Minister's Briefing LTEP |  |  | Update on Modules |  | Monday Sept 18 - Friday Sept 22 | Layout / Translation / Print
[5 empty] | (4:30-5:30pm) |  |  |  |  | Monday Sept 18 - Friday Sept 22 | Module and technical briefing deck development
TBD - Communications Products
1900-01-23 |  | 25 |  | 26 | 27 |  | 28 | 28 | 1900-01-29 | 2017-09-25
|  | LRC |  | Minister's Briefing LTEP |  |  |  | Update on Modules |  | Monday Sept 25 - Friday Sept 28 | Layout / Translation / Print
|  | TBD |  | (3:30-4:30pm) | [5 empty] | Monday Sept 25 - Friday Sept 28 | Module and technical briefing deck development
|  | Legislative Changes |  | TBD
LTEP DRAFT CALENDAR - OCTOBER 2017
1 |  | 2 |  | 3 | 4 |  | 5 | 6 | 7 | 2017-10-02
[5 empty] | CABINET- Tabling |  |  | Finalize Modules |  | Monday Oct 2 - Friday Oct 6 | Layout / Translation / Print
[5 empty] | LTEP Document and Directives |  |  |  |  | Monday Oct 2 - Friday Oct 6 | Module and technical briefing deck development
[10 empty] | Friday Oct 6 | Finalize Modules and technical briefing deck
1900-01-07 |  | 1900-01-08 |  | 1900-01-09 | 1900-01-10 |  | 1900-01-11 | 1900-01-12 | 1900-01-13 | 2017-10-09
[10 empty] | Monday Oct 9 - Friday Oct 13 | Layout / Translation / Print
1900-01-14 |  | 1900-01-15 |  | 1900-01-16 | 1900-01-17 |  | 1900-01-18 | 1900-01-19 | 1900-01-20 | 2017-10-16
[10 empty] | Monday Oct 16 - Tuesday Oct 17 | Layout / Translation / Print
[10 empty] | Wednesday Oct 18 | Potential LTEP Release
Grey = | DM Briefings |  | Purple = | DM, CoS Briefings | Light Green = | LRC
Orange = | Min. Briefings |  | Green = | Cabinet | Pink = | LTEP Document Related | [5 empty] | V41 Last Updated August 17, 8pm
Yellow = | PO Briefings |  | Blue = | Treasury Board
Potential LTEP Release
Sign-Off
Layout/Translation/Print
Layout/Translation/Print
Copy Edit
Layout/Translation/Print
Layout/Translation/Print

## Sheet1 (hidden)
Tasks | Start Date | Duration (Days) | End Date
Themed Briefings | 2017-03-06 | 34 | 2017-04-09
LTEP Document Drafting | 2017-04-09 | 42 | 2017-05-21
Cabinet Approvals | 2017-05-15 | 6 | 2017-05-21
Formal Sign-Off | 2017-05-21 | 5 | 2017-05-26
Production and Communications Development | 2017-05-27 | 13 | 2017-06-09
Document Release and Technical Briefing | 2017-06-10 | 6 | 2017-06-16