## Colour Calendar
SEPTEMBER 2013
Sunday |  | Monday |  | Tuesday | Wednesday | Thursday | Friday | Saturday
2013-09-01 |  | 2013-09-02 | Labour Day | 2013-09-03 | 2013-09-04 | 2013-09-05 | 2013-09-06 | 2013-09-07
Last updated: |  |  |  | Burlington - Consults (DM) | Directors' Brainstorm (9-12) |  | Directors' Brainstorm (9-12)
Sep 15 at 12:10 PM | [6 empty] | CAB Deck to ADMs
MO - PO Deck (3-4:30)
[5 empty] | DM - Themes / Outcomes / | DM - Demand | DM - Conservation (RE)
[5 empty] | Pricing (RA+E) | Forecast (OPA+E+RE) | DM - Nuclear (E)
2013-09-08 |  | 2013-09-09 | House Resumes | 2013-09-10 | 2013-09-11 | 2013-09-12 | 2013-09-13 | 2013-09-14
|  | En Route to Kenora |  | SSM - Consults (ADM) | DM - Renewables incl. Tx | Whitby - Consults (DM) | Ottawa - Engagement
|  |  |  | Kenora - Consults (DM) | Considerations (RE+E) |  | MO - Demand Forecast (8-9:30)
[5 empty] | En Route to Toronto | CAB Deck to DMO | MO - Conservation (3:30-5)
DM - Tx + N of Dryden (E)
DM - Innovation + Storage (E)
2013-09-15 |  | 2013-09-16 |  | 2013-09-17 | 2013-09-18 | 2013-09-19 | 2013-09-20 | 2013-09-21
|  | Cabinet Deck to DM (noon) + MO |  | MO - Nuclear (10-12) | MO - Thermal + CHP (4:15-5) | DM - Renewables Round 2 (12:30-1:30) | Binder of Decks to DM + MO
|  | MO - Cabinet Deck (1-1:30) |  | DM - Clean Import (12-1) | MO - Aboriginal (6-7) | DM - Conservation Round 2 (1:30-2:30) | - Demand
|  | MO - Tx + N of Dryden (1:30-2:15) |  | M. Brief - Cabinet Update (3-5) |  | M. Approved Cabinet Deck Due | - Conservation
|  | MO - Innovation+ Storage (2:15-3) |  |  |  |  | - Nuclear
|  | DM - Thermal + CHP (4-5) |  |  |  |  | - Renewables
|  | MO - Renewables (5:30-6:30) |  |  |  |  | - Tx + N. of Dryden
|  | DM - Aboriginal(6:30-7:30) |  |  |  |  | - Innovation + Storage
- Thermal + CHP
- Aboriginal
|  | EBR posting closes |  |  |  |  | - Clean Imports
EBR Summary List + Top 10 to DMO
2013-09-22 |  | 2013-09-23 |  | 2013-09-24 | 2013-09-25 | 2013-09-26 | 2013-09-27 | 2013-09-28
|  | MO - Clean Import (11-11:30) |  | DM - Sector Efficiences (11-12) | CABINET UPDATE (12-2:30) | Innovation Session (DM)
|  | DM - Nuclear (5-5:45) |  | DM - Oil + Gas (12-1) | Innovation Dinner (DM+M) | M. Brief - Demand (1:30-2)
|  |  |  | MO also available 3-6 |  | M. Brief - Conservation (2-2:30)
M. Brief - Nuclear (2:35-3:30)
M. Brief - Renewables (3:35-4:05)
|  | LTEP Doc - Conservation Section |  |  | LTEP Doc - Conservation Section to MO | M. Brief - NW Transmissions (4:05-4:30)
M. Brief - Smart Grid (5:15-5:45)
|  | to DM |  |  |  | M. Brief - Natural Gas Generation (5:45-6:15)
|  | LTEP DRAFT CALENDAR -AUGUST 2017 | [6 empty] | LTEP DOCUMENT TRACKING
1900-01-19 |  | 21 |  | 22 | 23 | 24 | 25 | 1900-01-25 | 2017-08-21
|  | EBR Frequency Regulation |  |  | PO / CO / MO Edits Due | CO / PO Comms Briefing | LTEP Document to writer |  | Monday Aug 21 | Receive next draft of LTEP document for review
|  | Posting Closes |  |  |  | Communications Plan Discussion |  |  | Wednesday Aug 23 | PO / CO / MO edits due to LTEP document
|  | Receive Draft of LTEP Document | [6 empty] | Friday Aug 25 | LTEP document to writer for revision
1900-01-26 |  | 28 |  | 29 | 30 | 31 | 1 | 1900-01-01 | 2017-08-28
|  | Next Draft of LTEP Document |  | LRC | Share LTEP with CO / PO / MO | CABINET | LTEP Document to Writer |  | Monday Aug 28 | Receive next draft of LTEP document for review
|  |  |  | LTEP Frequency Regulation |  | LTEP Part 2, SGF, Frequency Reg |  |  | Monday Aug 28 - Wednesday Aug 30 | Partner Minsitry review of LTEP document (one day)
[9 empty] | Wednesday Aug 30 | Share LTEP document with CO / PO / MO for final review
[9 empty] | Friday Sept 1 | LTEP document to writer for revision
LTEP DRAFT CALENDAR - SEPTEMBER 2017
3 |  | 4 |  | 5 | 6 | 7 | 8 | 9 | 2017-09-04
|  |  |  | Final Draft of LTEP Document | CO / PO Briefing LTEP |  | Pens Down LTEP Document |  | Tuesday Sept 5 | Receive final draft of LTEP document for review
[5 empty] | (3-4pm) |  |  |  | Wednesday Sept 6 | PO / CO / MO provide final comments on LTEP document
[5 empty] | LTEP Document and Communications |  |  |  | Friday Sept 8 | Pens Down on LTEP document
CO/PO/MO Final Comments due
1900-01-09 |  | 1900-01-10 |  | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 2017-09-11
[9 empty] | Monday Sept 11 - Tuesday Sept 12 | Ministry of Energy sign-off on LTEP document
[9 empty] | Wednesday Sept 13 - Friday Sept 15 | Layout / Translation / Print
1900-01-16 |  | 1900-01-17 |  | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 2017-09-18
[9 empty] | Monday Sept 18 - Friday Sept 22 | Layout / Translation / Print
1900-01-23 |  | 25 |  | 26 | 27 | 28 | 28 | 1900-01-29 | 2017-09-25
|  | LRC - Legislative Changes | [6 empty] | Monday Sept 25 - Friday Sept 28 | Layout / Translation / Print
Net metering and Green Button
LTEP DRAFT CALENDAR - OCTOBER 2017
1 |  | 2 |  | 3 | 4 | 5 | 6 | 7 | 2017-10-02
[5 empty] | CABINET- Tabling |  |  |  | Monday Oct 2 - Tuesday Oct 3 | Layout / Translation / Print
[5 empty] | LTEP Document and Directives |  |  |  | Wednesday Oct 4 | Table final LTEP and implementation directives
1900-01-07 |  | 1900-01-08 |  | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 2017-10-10
[9 empty] | Tuesday Oct 10 - Friday Oct 13 | Potential LTEP Release
1900-01-14 |  | 1900-01-15 |  | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20
Yellow = | CO / PO Briefings |  | Pink = | LTEP Document Related
Green = | Cabinet | [9 empty] | V41 Last Updated August 17, 8pm
Light Green = | LRC
Potential LTEP Release
Ministry of Energy Sign-Off
Layout/Translation/Print
Layout/Translation/Print
Layout/Translation/Print
Layout/Translation/Print
Partner Ministry Review (Date TBD)

## Sheet1 (hidden)
Tasks | Start Date | Duration (Days) | End Date
Themed Briefings | 2017-03-06 | 34 | 2017-04-09
LTEP Document Drafting | 2017-04-09 | 42 | 2017-05-21
Cabinet Approvals | 2017-05-15 | 6 | 2017-05-21
Formal Sign-Off | 2017-05-21 | 5 | 2017-05-26
Production and Communications Development | 2017-05-27 | 13 | 2017-06-09
Document Release and Technical Briefing | 2017-06-10 | 6 | 2017-06-16