## Sheet1
OPCD - Fair Hydro Ac |  |  |  | high priority
Risk and Issue Log |  |  |  | medium priority
low priority
ID# | Request | Purpose | Date raised | Expected output | Timeline to complete | Date of update | Date closed | Comments (Additional information)
1 | Provide comments on IESO memo re: RRA accounting | Strengthen position/identify risks wrt RRA accounting | 2019-04-01 | Comments on IESO memo | Comments sent Thursday April 20
2 | Document identified possible indicators of control from various legal documents | Identify indicators for and against control by OPG/other entity | 2019-04-01 | List of identified control indicators and possible impact |  |  |  | include discussion with OPG EY team; considerations include: guarantees including market disruption guarantee (i.e. commercial paper placed before bond deal - Province step in or immediately have it become due and payable), termination clause,kick out rights, other entities involved in transaction (OEB control); what happens if OPG can't buy the RRA asset?
3 | Read various legal documents | General comments or issues related to document | 2021-04-01 | Comments on document |  |  |  | Comments on consultation v3 sent April 22
4 | Consider structure of OPG Trust as SPE under OPG getting picked up by Province under modified equity and research other examples | Identify other examples of organizations consolidating through a GBE that would not be considered GBEs themselves | 2019-04-01 | Discussion/notes
5 | Map out entries at consolidated level under scenario where IESO is not permitted to record an RRA | Understand possible impact on public accounts | 2019-04-01 | Journal entries and possible impact |  |  |  | for example, consider PS3070.08 and PS3420 - interorganizational gains on assets remaining in consol entity are eliminated (reduction in investment in GBE?)
6 | Understand the transition of asset from RRA in IESO to Intangible in OPG | Identify possible risk with respect to the RRA accounting from these transactions (i.e. because OPG accounts as intangible asset - include in discussions with OPG team); also consider accounting at the provincial level for these transfers | 2019-04-01 | Discussion/notes |  |  |  | - current acctg is that it does not meet criteria of financial asset for OPG because buying from a ratepayer class and not an RRA because no costs incurred by Trust which leaves intangible but this then becomes an issue for the financing costs - also, how will they derecognize
7 | Document flow of interest and existence of related RRA and subsequent transfer to intangible asset and related impact from interest perspective | Strengthen position/identify risks wrt accounting | 2019-04-01 | Discussion/notes
8 | Consider impact of clean energy charge being deemed an unconstituational tax | Determine possible accounting impact on public accounts | 2019-04-01 | Discussion/notes
9 | Reach out to global network for examples of other PS entities following RRA (following standards other than US GAAP and IFRS) | Support posifor RRA in public sector financial statements | 2019-04-01 | Discussion/notes | in progress | sent email April 17 | No examples identified to-date
10 | Consider accounting if in, say 5 years, new legislation comes along that wipes out the structure | Impact to the public accounts | 2019-04-01 | Discussion/notes