## Table of Contents
Business Case Template: Conservation Programs & Pilots
For: New province-wide programs, changes to province-wide programs, new local/regional programs, changes to local/regional programs & LDC innovation fund pilots
Table of Contents:
Links:
| Legal Terms | Regional/Local programs only (program rules)
1 | Guidelines
2 | Submission Details
3 | Summary Page
4 | Review Sheet
5 | Similar Programs or Pilots Concepts in Ontario
6 | Gas & Water Collaboration
7 | Market Characterization
8 | Energy Efficient Measures
8a | EE Measures - Custom
9 | Budget
10 | Cost Effectiveness
11 | Risk Analysis
12 | Measurement & Verification
13 | Program Rules | Province-wide/Regional/Local programs only
14 | Value-Added Central Services | Province-wide/Regional/Local programs only
15 | Project Milestones | LDC Innovation Pilots only
16 | Participant Agreement | Only if necessary based on design of program/pilot
17 | Definitions | Not applicable to Province-wide
18 | Available Resources
Powered by:

## Legal Terms
Legal Terms (Regional/Local Programs ONLY)
Local/Regional Program Rules
If this proposed Program is accepted by the IESO (at its sole discretion), the following sections only, will be Local/Regional Program Rules for the purposes of the Energy Conservation Agreement. The LDC shall do all things necessary to deliver the Program as described in the table below.
Tab 6, s. 2a |  | Gas collaboration
Tab 7, ss. 1(a) and (b) |  | Participant and Facility Eligibility Criteria
Tab 7, s. 7 |  | Participant Enrolment
Tab 8, s. 1a (column C + D) |  | Eligible Measures
Tab 8, s. 1b |  | Project Eligibility Requirements
Tab 8, s. 2 |  | Participant Incentives only
Tab 8a, s. 6 |  | Custom Measure(s) Description
Tab 9, s. 1 |  | Program Budget (Central Services Costs only)
Tab 9, s. 2a |  | Ineligible costs
Tab 9, s. 3 |  | P4P Option
Tab 9, s. 3a |  | P4P Rate
Tab 12 |  | Measurement & Verification
Tab 12, ss. 3(a), 3(b) and 4 |  | Measurement & Verification (Data Collection and QA/QC)
Tab 14, s. 1 |  | Central Services
Tab 16 |  | Participant Agreement
Tab 17 |  | Definitions
The following sections will not for part of any Program Rules, and for clarity may not be referred to in determining whether the LDC has met the Program requirements, is eligible for funding or payment or whether savings may count towards the CDM Target.
Tab 1 | Guidelines
Tab 2 | Submission Details
Tab 3 | Summary Page
Tab 4 | Review Sheet
Tab 5 | Similar Pilot or Program Concepts in Ontario
Tab 6 | Gas & Water Collaboration (other than s. 2a)
Tab 7 | Market Characterization (other than s. 1a, s. 1b and 7)
Tab 8 | Energy Efficiency Measures (other than s. 1a (column C+D), s. 1b & s.2)
Tab 8a | EE Measures - Custom (other than s. 6)
Tab 9 | Budget (other than s. 1 (Central Services Costs), s. 3, s. 3a)
Tab 10 | Cost Effectiveness
Tab 11 | Risk Analysis
Tab 13 | Program Rules
Tab 14 | Central Services (other than s. 1)
Tab 15 | Project Milestones
Appendix A | Work Back Structure for Central Services
Appendix B | Scope of Work Template for Central Services

## 1. Guidelines
1 | Guidelines for Completing this Template:
Things to keep in mind when completing this business case template:
1 | Please complete all sections that apply to your program/pilot (sections not applicable to programs or pilots are highlighted)
2 | Add space and rows as needed throughout the document in text boxes and tables
3 | All review criteria at the top of each tab have to be deemed satisfactory (if applicable to your program/pilot) for the business case to be approved by the IESO.
4 | Any change made (even a small one!) to a prescriptive measure on the Measures & Assumptions List automatically categorizes that measure as a custom measure and requires necessary documentation.
5 | Substantiating figures in the business case: please be sure to use the sources in the "Available Resources" tab, primary market research, program evaluation results from other similar jurisdictions, and/or peer reviewed journal articles
6 | Any change made to this program while in-market that has an impact on the program rules ("Legal Terms" tab) will require a re-submission of this business case for approval. Changes to pilots will be captured in the mid-point and final reports discussed in the "Project Milestones" tab. (Changes in budget that exceed the contracted total will need to go through a contract amendment process.)
7 | Please add attachments as required to substantiate the figures you have included in your business case. If you do add an attachment, please add a note under the appropriate question in this template.
8 | This business case is submitted pursuant to the Energy Conservation Agreement (ECA), and if accepted (at the IESO's sole discretion) will be subject to it. Please review the ECA to ensure your proposal meets the ECA requirements, including:
| 1 | Article 4 | FUNDING AND PERFORMANCE INCENTIVES
| 2 | Article 8 | PARTICIPANT AGREEMENTS
| 3 | Article 9 | EVALUATION, MEASUREMENTS AND VERIFICATION AND REPORTING REQUIREMENTS
| 4 | Article 10 | RECORDS AND AUDITS
| 5 | Schedule D | COST EFFECTIVENESS FOR PURPOSES OF ARTICLE 5
| 6 | Schedule F | PARTICIPANT AGREEMENT PROVISIONS
| 7 | Schedule G | EM&V REQUIREMENTS
Additionally subject to the following Rules and Guidelines:
|  | See: | http://www.ieso.ca/Pages/Conservation/Conservation-First-Framework/LDC-Tool-Kit.aspx
| 8 | RULES | DATA AND REPORTING REQUIREMENT RULES
| 9 | RULES | SETTLEMENT INFORMATION REQUIREMENTS RULES
| 10 | RULES | PAY FOR PERFORMANCE RULES
| 11 | GUIDELINE | ELIGIBLE PROGRAM DELIVERY EXPENSES GUIDELINE
| 12 | GUIDELINE | EVALUATION GUIDELINE
Attachments Needed: Cost Effectiveness Tool, Program Rules (province-wide only), Central Services Gantt Chart, Central Service Statement of Work
Program design pre-consultation:
Form available on the LDC Tool Kit page (send to LDC.Support@ieso.ca):
http://www.ieso.ca/Pages/Conservation/Conservation-First-Framework/LDC-Tool-Kit.aspx
Optional: completing request for program design pre-consultation from the IESO
Recommended: Pre-consultation with IESO EM+V to develop EM+V plan (ensure all elements of the program/pilot can be evaluated)
Available: IESO Training for business case template completion

## 2. Submission Details
2 | Submission Details
Please complete all sections in grey below:
1 | Name of Program/Pilot: | Smart RT for Small and Mid-Size Business | (If you are re-submitting a business case, please ensure the name is identical to your earlier submission)
2 | Date Submitted: | 2016-07-29 | (DD-Mon-YYYY)
3 | Type of Program/Pilot: | (Add an "x" next to the category that applies to this submission in grey section below)
New province-wide program
Change to province-wide program
| New Local Program | x
Change to Local Program
New Regional Program
Change to Regional Program
LDC Innovation Fund Pilot
4 | Program/Pilot Details: | (Add an "x" to the category that applies to this submission in grey section below)
| Collaboration with gas utilities | x
Collaboration by multiple LDCs
Pay for Performance program
Program/Pilot targets constrained areas (identified through regional planning)
Measures focused on peak demand reductions
Minor changes to existing province-wide programs
4 | Lead LDC Contact:
| Name: | Matt Jones
| Phone: | 416.542.3069
| Email: | MJones2@TorontoHydro.com
| LDC: | Toronto Hydro Electric Systems Limited
5 | Other LDCs: | (Please list all LDCs (or working group for province-wide) delivering this pilot/program below, add rows if needed)
| LDC | Name (Main Contact) | Email (Main Contact)
| Oakville Hydro | Matt Jones | MJones2@TorontoHydro.com
Please submit this completed business case to: CDMplans@ieso.ca

## 3. Summary Page
3 | Summary Page
Please complete all sections in grey below…
Program/Pilot Description:
1 | Please provide a description of the proposed program (or change to a program) or pilot by answering the questions below:
1a | Please describe the program/pilot objective below (or objective for a program change): This is a description of the program/pilot "intervention" including targeted technology/behaviour change and Participant Incentives (and any equipment decommissioning)
1b | Please provide a brief description of the target market for this program/pilot below:
Also, please mark an "x" beside the customer segment(s) targeted by your program:
Residential
Low-income
| x | Small business
| x | Commercial (including multi-family)
Agricultural
| x | Institutional
| x | Industrial
1c | Please indicate the delivery method(s) for this program/pilot:
| x | Direct Install
| x | Rebate
Instant Discount
Upstream
| x | Midstream
Audit/Assessment/Energy Report (Benchmarking)
2 | When is the proposed program or pilot anticipated to be in market?
If your in-market date changes after your program or pilot has been approved, please notify LDC.Support@ieso.ca with the title "Change to Business Case"
| 2017-01-02 |  | (DD-Mon-YYYY)
3 | When is the proposed program or pilot anticipated to end?
| 2020-12-31 |  | (DD-Mon-YYYY)
[The following question applies to regional/local programs and pilots only]
4 | Please describe the potential for a scale-up to a province-wide program (and/or local/regional program for pilots) in the space provided below:
Program/Pilot Summary Chart:
5 | Please complete the table below based on the output of the Cost Effectiveness Tool and your analysis from sections 5-12 of this template:
|  |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2016-2020 TOTAL
Program Budget - Fixed |  |  |  | 471441.29 | 487661.93 | 407551.61 | 377551.61 | 1744206.44
Program Budget - Variable |  |  |  | 1607466.08 | 2411199.13 | 2009332.6 | 2009332.6 | 8037330.41
Total Program Budget |  |  | 0 | 2078907.37 | 2898861.06 | 2416884.21 | 2386884.21 | 9781536.85
% of LDC CFF Budget (local/regional programs only) |  |  |  | 2.535% | 3.971% | 3.404% | 2.486% | 2.445%
Expected KWh savings (the results in the "Plan" tab of the CE Tool) |  |  | 0 | 4827930.0669 | 7241895.1003 | 6034912.5836 | 6034912.5836 | 24139650.3344
% of LDC CFF Target (local/regional programs only) |  |  |  | 1.454% | 2.932% | 2.579% | 2.018% | 1.532%
Total Resource Cost (TRC) Test Result |  |  |  | 3.139 | 3.4717 | 3.5663 | 3.6939 | 3.4745
Program Administrator Cost (PAC) Test Result |  |  |  | 2.673 | 2.9516 | 3.0321 | 3.1397 | 2.9549
Levelized Unit Energy Cost (LUEC) |  |  |  | 0.040766 | 0.037897 | 0.037915 | 0.037445 | 0.038383
Total Estimated # of Participants |  |  |  | 3211.0321 | 4816.5482 | 4013.7902 | 4013.7902 | 16055.1606
6 | Please indicate below whether the proposed program or pilot is designed to be: (Add an "x")
| x | Full Cost Recovery (FCR)
Pay for Performance (P4P)
Engage small business customers in dialog and action for energy conservation and demand management
Cost-effectively achieve new maximum net energy savings for Toronto Hydro and Oakville Hydro’s 2015-2020 target
Inspire new activity in the small scale energy management system and services industry
Build channel capacity in the industry
Compatible with other current or future Save on Energy programs such as Retrofit, Roof-Top Replacement, Enbridge VOD
Available for Local DR program efforts
Program targets all small to mid size businesses with roof-top units. Restaurants, small offices, big box stores as well as all other small businesses heat and cool with mostly inefficient rooftop units This broad program will provide excellent savings for all segments of the C&I market.
The program is applicable to all roof-top applications, therefore scaling would be straightforward.

## 4. Review Sheet
4 | Review Sheet
TO BE COMPLETED BY IESO: |  | Program/Pilot Type: |  | INSERT from 'Submission Details' - Question 3
|  | Program/Pilot Details: |  | INSERT from 'Submission Details' - Question 4
|  | IESO Completeness Check (Yes/No)1 | IESO Review Stage (Yes/No/NA)2 | If no in column D, IESO detailed comments below (teams to comment identified):
| Attachments (check for all relevant attachments: CE Tool, Program Rules (province-wide), Central Services Gantt Chart and Scope of Work (if requested)) | INSERT | N/A | [PPS]
2 | Submission Details | INSERT | INSERT | [PPS]
3 | Summary Page | INSERT | INSERT | [MT/EMV]
5 | Similar Programs or Pilots | INSERT |  | [MT]
6 | Gas & Water Collaboration | INSERT |  | [MT]
7 | Market Characterization | INSERT |  | [MT]
8 | Energy Efficient Measures | INSERT |  | [MT]
8a | EE Measures - Custom | INSERT |  | [EMV/ENG]
9 | Budget | INSERT |  | [MT/PPS-if P4P or Central Services]
10 | Cost Effectiveness | INSERT |  | [MT]
11 | Risk Analysis | INSERT |  | [MT]
12 | Measurement & Verification | INSERT |  | [EMV]
13 | Program Rules (only province-wide/regional/local) | INSERT |  | [Legal]
14 | Value-Added Central Services (only province-wide/regional/local) | INSERT |  | [PPS]
15 | Project Milestones (only pilots) | INSERT |  | [PPS]
16 | Participant Agreement | INSERT |  | [MT/Legal]
17 | Definitions | INSERT |  | [Legal]
|  |  | Program/Pilot Review - RESULT --> | ADD RESULT ("Approved", "Not approved" or "Re-submit")
|  |  | Date: | [DD-Mon-YYYY]
IESO Final Recommendation:
| IESO Approvals: |  | Signature |  | Date
IESO Market Transformation Manager Approval:
IESO Conservation Performance Director Approval:
IESO Conservation and Corporate Relations VP Approval:
Notes:
1 | All sections must be complete to move onto IESO review stage
2 | All sections must be approved by the IESO or the LDC receives an invitation to re-submit business case (will include notes for each non-approved section above)

## 5. Similar Programs or Pilots
5 | Similar Program or Pilot Concepts in Ontario
| Review Criteria | IESO Staff to complete this box
Section Approved? (Yes/No):
Yes/No
Proposed program or pilot is not duplicative of any other program or pilot in Ontario
If No -->
The proposed program/pilot solution cannot be adequately addressed by existing programs or pilots (element(s) of an existing program/pilot have to be changed to accommodate specific LDC territory needs (target market, incentive, delivery model) or existing program cannot be changed quickly enough to take advantage of a market opportunity)
Section 5: LDC Questions (please complete all grey sections below)
1 | Is this proposed program or pilot noticeably and substantively different than all province-wide programs, approved or in-market local/regional programs and pilots in Ontario?
Please complete the following table to answer this question. A program/pilot is considered a duplicate of another program/pilot if all of the elements below (incentive, solution, customer experience) are the same - all "no" answers below)
If no…
| Is your program or pilot different, considering… |  |  |  | Yes/No | Which program/pilot is similar? | How is it similar?
| …the incentive? |  |  |  | yes
| …the solutions? (measures, delivery model, etc.) |  |  |  | yes
| …the customer experience? |  |  |  | yes
1a | [1 a-c: Local/Regional programs only] Is this proposed local or regional program an adaptation of an already approved local or regional program in another LDC's territory?
Please mark an "x" in appropriate box below.
|  | x | No | (go to question 2)
Yes
If yes, name of program:
1b | If yes, is this proposed local/regional program in any way different from the already approved local/regional program?
Please mark an "x" in appropriate box below.
|  |  | No | (go to question 2)
Yes
If yes, define changes:
1c | If yes, have the LDC(s) who have an already approved local or regional program similar to this program been notified of the changes you are proposing?
No
Yes
If yes, are all LDCs in agreement?
If you indicated 'no' to ALL criteria in the table above, please answer the following question…
2 | Why can't a change to an existing program in Ontario achieve the objectives of this proposed program or pilot?
3 | For ease of review purposes, if applicable, please indicate below which pilot this province-wide/regional/local program is based on:
Notes:
The Minister’s Direction of March 31, 2014 includes a requirement that “the IESO shall seek to approve unique Local Distributor CDM Programs that avoid marketplace confusion and ensure the prudent use of funds by avoiding duplication of Province-Wide Distributor CDM Programs”. In assessing whether something is duplicative or not, the guiding principle is that if either (or both) the solution or the customer experience offered by a local program is noticeably and substantively different than what is offered by current province-wide or regional distributor programs, then the local program is not a duplicate.
Please refer to the “Avoiding Duplication Guideline” for assistance in completing the following set of questions.
Different incentives and channel strategy than the Retrofit program. Limited take up of smart wifi thremostats for roof top units with any current program offer.
The program follows pilots by Toronto Hydro - Advanced Roof Top (RTU) Control Pilot Application and Gridsaver (aka CEMLC).

## 6. Gas & Water Collaboration
6 | Gas & Water Collaboration
| Review Criteria |  | IESO Staff to complete this box
Section Approved? (Yes/No/NA):
Yes/No/NA
Have best efforts been made by the LDC to collaborate with gas distributors in the design of this program or pilot? (Select "NA" if no impact on gas). If no, please provide documentation to support efforts (meeting notes, email communications).
Section 6: LDC Questions (please complete all grey sections below)
Note: The IESO will not approve an electric only program in an area where a similar gas program is being delivered unless the LDC can demonstrate their best efforts to broker a coordinated program with gas utilities have not yielded results. If any collaboration issues arise and you think it would be beneficial to involve the IESO, please complete the pre-consultation form and submit to LDC.Support@ieso.ca.
1 | This proposed program or pilot has an impact on gas consumption:
(Add an "x" next to either yes or no below)
|  | No | (Please skip to question 3)
| x | Yes | (Please complete go to question 1a)
1a | There is an in-market Union Gas/Enbridge program that aligns with this proposed program/pilot:
No
| x | Yes | (If yes, it is required that best efforts be made to collaborate with Union Gas/Enbridge on this proposed pilot/program)
If yes, please provide the name of the Union Gas/Enbridge program below:
Ventilation on Demand Program from Enbridge is the natural extension of this Smart wifi thermostat program. No conflict, great up sell opportunity for certain types of architypes.
2 | This proposed program or pilot will include collaboration with one or more gas distributors:
(Add an "x" next to either yes or no below)
|  | No | If no, please answer question 2b
| x | Yes | If yes, please answer question 2a
2a | The LDC will collaborate will Union Gas/Enbridge as follows: (a program rule)
2b | Please explain why you are not collaborating with a gas distributor and provide a detailed description of the efforts by your LDC to collaborate:
3 | If your proposed program or pilot has associated water savings, please indicate below if you are collaborating with a water utility or municipality (include name of organization and details of collaboration):
Notes:
The Minister’s Direction of March 31, 2014 includes a requirement to “require Distributors, where appropriate, to coordinate and integrate Province-Wide Distributor CDM Programs and Local Distributor CDM Programs with natural gas distributor (‘Gas Distributors’) conservation programs to achieve efficiencies and convenient integrated programs for electricity and gas customers” (S.3.5.xi). Further, the direction requires “Distributors, where appropriate, to coordinate and integrate low-income Province-Wide Distributor CDM Programs and Local Distributor CDM Programs with Gas Distributor low-income conservation programs”(S3.5.xii).
The purpose of this section is to establish how the proposed program satisfies this requirement. Prior to submitting this application you are responsible for establishing this potential including having consulted with the appropriate Gas Distributor. Please refer to the "Gas Collaboration Guideline" for further detail.
The LDC, or its Service Provider, will offer the Participant the opportunity to upgrade to Enbridge's Ventilation on Demand Program, where available and where it is applicable to the Participant.
n/a

## 7. Market Characterization
7 | Market Characterization
| Review Criteria | IESO Staff to complete this box
Section Approved? (Yes/No):
Yes/No
Is target market selected is appropriate for program/pilot concept?
Are projected participation levels reasonable and substantiated? (based on either a) market penetration by a similar program in the LDC's service territory, b) market penetration by a similar program in another similar (economically, climate) jurisdiction, and/or c) primary market research with residents/businesses in the LDC's service territory)
Is the delivery model chosen appropriate for this program/pilot concept? ( i.e. the delivery model has been proven effective in Ontario or other similar jurisdictions)
The LDC has undertaken stakeholder/customer engagement or market research to determine viability of the program? (Pilot concept viability can be based on pilot results from other similar jurisdictions.)
Section 7: LDC Questions (please complete all grey sections below)
1 | Please describe the target market eligible for this proposed pilot or program below: (Examples of elements to include could be: region, sector, subsector, facility type, type of customer (i.e. low income, first nations, small/medium/large business etc.), building or dwelling characteristics (i.e. facility size (KW), heating type, Wi-Fi access, age, etc.)
1a | Please list the eligibility criteria to be a Participant: (a program rule)
1b | Please list the eligibility criteria for the Facility to participate in the program or pilot: (a program rule)
2 | Please describe below why you have chosen this target market for your proposed program or pilot:
3 | Please summarize the eligible market size and forecasted participation by completing the table below: (If year not applicable to your proposed program or pilot, please add "NA" in the table.)
|  |  | Total (# ) | Data Sources2 |  | Description of Assumptions Made
| Total Population (Sector-level) |  | 80275.8032 | Toronto Hydro independent study of roof top units. Based on extrapolation of new Roof Top unit sold in Ontario. |  | Average roof-top units are replaced every 25 years. Toronto has higher share of larger units than rest of Ontario. (see RTU Assumption Worksheet tab for full analysis)
| Total Eligible Population (Participants at the project level): |  | 80275.8032
Projected Participation (# of RTUs): (based on the % of the eligible market who has indicated they would be interested in participating in this proposed program/pilot and/or historical participation in a similar program/pilot and/or participation levels from a similar jurisdiction (economically and climate))
2016
| 2017 |  | 3211.0321 | Lessons learned from TH pilots
| 2018 |  | 4816.5482
| 2019 |  | 4013.7902
| 2020 |  | 4013.7902
| 2016-2020 |  | 16055.1606 | Note: most costs are variable, therefore any incr or decrease will not materially impact CE results (TH takes the performance risk) |  | Assumes 20% of eligible customers will participate in base program; 4% in Occ Sensors; and 1% Vent on Demand.
1 Total Eligible Population = (Total Population) - [less] (Ineligible buildings, dwellings, customers (can include past participants))
2 See "Available Resources" tab for a list of data sources (this could include Stats Can, MPAC, billing data, etc.)
4 | Please include your calculations for the eligible population total below (All steps in your calculation from total population to eligible population): For example, if I'm offering a smart thermostat program my calculation would start with all residential households AND remove those without central heating and/or cooling AND remove those without a Wi-Fi connection AND remove those who already have a smart thermostat (either by natural purchasing or past program/pilot participation)
5 | Please describe the primary stakeholder/customer engagement/market research you have conducted to substantiate projected program or pilot participation below ("concept" testing research to determine if/how many customers would be interested in participating in this program/pilot): (Include: who conducted the research, methodology used, sample size and key findings)
6 | Please describe the delivery model(s) you have chosen below and why you have chosen that model (i.e. midstream, direct install, rebate/incentive to end-user, etc.)
7 | The LDC will enroll Participants as follows: (a program rule)
8 | Please complete the table below to describe the role of each party involved in delivering the proposed program or pilot: (Please add "NA" if not applicable to your proposed program or pilot)
| Delivery party |  | Role |  | Describe contractual relationship
| LDC |  | Delivery Funder |  | Contract counterparty for all agreements
| Gas Distributor |  | Co-Marketer |  | MOU for co-marketing Ventilation on Demand with SmartRT
| Manufacturer (Roof Top) |  | Mid-Stream delivery agent |  | N/A
| Contractor |  | Delivery Agent |  | Contract with TH (or Integrator) to deliver program to customers
| Distributor |  | Mid-Stream delivery agent |  | N/A
| Fulfillment Services |  | optional |  | LDC may choose to contract or internalize
| Integrator (optional) |  | Intermediary between TH and contractor |  | Under contract with TH to deliver program through Trade Ally network.
| Smart Thermostat Supplier |  | Marketing |  | Suppliers will need to have their product qualify for eligibility in Smart-RT
All non-Residential customers who have Air Conditioning suppled by a packaged terminal (e.g.. roof-top) unit 4 tonnes or larger. [Acceptable alternative is any conditioned space over 1,500ft2 services by a packaged terminal AC unit]
Participant must be a non-residential account in the LDC service area.
Except where mid-stream supplier is providing a smart thermostat with a new packaged terminal AC unit, Participant must commit to an assessment report completed by the LDC's service provider(s) and all necessary repairs must be complete as identified by LDCs assessment report.
Participant's facilities must be conditioned by at least one packaged terminal unit with air conditioning sized at 4 tonnes or higher [alternatively where tonnage not know conditioned space must be 1,500 ft2 or greater].
Market is underserved.
see RTU Assumption Worksheet
Two pilot programs were implemented by Toronto Hydro. Based on feedback from those summary reports, the expected participation level is justified.
Base program, occupancy sensors and ventilation on demand will be offered as a rebate direct to customer after assessment and direct install by Toronto Hydro contractor (to be RFP). A secondary take-up component mid-stream will allow distributors to supply SmartRT eligible thermostats with the sale of a new packaged roof top unit. Mid-Stream customers would apply directly or through the distributor (customer choice). Repairs and upgrades (SoE Retrofit Program possible) may be completed by the customers HVAC contractor or TH contractor.
Participants will register for SmartRT through the Toronto Hydro Portal.

## 7-8s RTU Assumption Worksheet
Program: | Smart RT Progarm
LDC: | Toronto Hydro
Date: | 2016-07-26 12:24
Market Potential | Market Size | Historical New Sales |  | For Business Case
| Year | Average Ontario Shippments/Yr. | Calculated Total RTU in Market | Estimated % of RTU in TH Service Area | Estimated Quantity of RTU in TH Service Area | 5t/10t/20t Quantities
| 4 ton | 2186.2346 | 54655.866 | 20% | 10931.1732
| 5 ton | 4099.19 | 102479.7488 | 21% | 21520.7472 | 32451.9204
| 7.5 ton | 3279.352 | 81983.799 | 21% | 17216.5978
| 10 ton | 1639.676 | 40991.8995 | 23% | 9428.1369
| 15 ton | 1421.0525 | 35526.3129 | 35% | 12434.2095 | 39078.9442
| 20 ton | 546.5587 | 13663.9665 | 40% | 5465.5866
| 25 ton | 327.9352 | 8198.3799 | 40% | 3279.352 | 8744.9386
| Total | 13499.9989 | 337499.9727 |  | 80275.8032 | 80275.8032
| Assumed Avg. Life of RTU in ON | 25
Market Adoption (for use in CE Tool) | Adoption Curve | 20% | 30% | 25% | 25% | 100%
| Year | 2017 | 2018 | 2019 | 2020 | Totals
| WEb Enabled Programmable Thermostat | 3211.0321 | 4816.5482 | 4013.7902 | 4013.7902 | 16055.1606
| OCCUPANCY SENSORS | 682.5068 | 1023.7602 | 853.1335 | 853.1335 | 3412.5341
| Demand Controlled Ventilation | 175.5018 | 263.2526 | 219.3772 | 219.3772 | 877.5088
"Other Costs" (for use in CE Tool) | unsuccessful assessment cost | 128441.2851 | 192661.9277 | 160551.6064 | 160551.6064 | 642206.4257
RTU Calcs | kWh/yr./ton | 947 | Estimated from manufacturers data sheets at run hours (mostly fan energy)
| kW/ton | 1.2 | Calculated from manufacturers data sheets for more efficient units (ie conservative basline)
| HOO | 4056 | Estimated from fan runtimes and from Prior Pilot Programs
| Total Estimated in ON | 337499.9727 | See above market analysis
| Estimated in TO | 80275.8032 | See above market analysis
| Savings Assumptions | %kWh Savings | %kW Cool Savings | Notes
Measures Costs/Savings | Repairs Savings | 0% |  | Repair savings not part of program design, no savings attibution for this effort
| T-Stat Savings (kWh) | 21% | 2% | Based on savings from Pilot Studies and engineered calcs of mostly fan operating time savings
| incr Occ. Sensor Savings (kWh) | 4% | 5% | Engineering calucations base on additional run time savings
| incr DCV Savings inc(kWh) | 15% | 10% | Toronto Hydro Pilot (reduced from 55% down to 40% for conservative savings estimate)
| T-Stat Savings (kW) | calculated in CE Tool
| Occ. Sensor Savings (kW) | calculated in CE Tool
| DCV Savings (kW) | calculated in CE Tool
| Measure Incremental Cost |  | Nominal Cost
| Assessment Cost | 100 | 100
| T-Stat $/Unit | 350 | 350 | incl assessment
| incr T-Stat W Occ. $/Unit | 550 | 900
| incr T-Stat, Occ., DVC | 2600 | 3500
| Measure Incremental Incentives |  | Nominal Incentive
| T-Stat Incentive | 350 | 350
| Incr Occupancy Sensor Incentive | 400 | 750
| Incr DCV Incentive | 1200 | 1950
CE Assumptions
| Measure Life Expectancy | 15 |  | Industry standard life for thermostat in commercial setting (note: replacements are typically with equal or better)
| NTG | 0.8 |  | 8 basis-point improvement over Retrofit NTG due to higher influence factor of new program
| Measure Incremental Savings per RTU |  | Nominal Savings
| T-Stat Per Project Savings | 1630.4119 | 1630.4119 | Calculated below
| Occ Sensor per Project Savings | 589.8457 | 2220.2577 | Calculated below
| DCV per project savings | 2262.2778 | 4482.5354 | Calculated below
Energy Savings Calculations |  |  |  | Baseline Energy Use |  | Program Pennetration Rate | [5 empty] | Energy Savings | [5 empty] | Incentive Amounts |  |  | Assessment Cost (non participant)
| Tonnage | mkt Share | Estimated Count in TO Mkt | kWh/yr. | Peak kW | T-stat Uptake | Occ Uptake | DCV Uptake | T-stat Count | Occ Count | DCV Count | T-Stat kWh Avoided | Occ kWh Avoided | DCV kWh Avoided | T-Stat kW Avoided | Occ kW Avoided | DCV kW Avoided | T-Stat | Incr Occ Sensors | incr DCV | % assessments not resulting in Tstat install | # non-participants | Addded Assessment Cost
| 4 | 16.19% | 13000.1301 | 49244492.7262 | 43680.4371 | 20% | 0% | 0% | 2600.026 | 0 | 0 | 2068268.6945 | 0 | 0 | 249.6025 | 0 | 0 | 910009.1053 | 0 | 0 | 0.4 | 1040.0104 | 104001.0406
| 5 | 30.36% | 24375.2439 | 115416779.827 | 102376.0243 | 20% | 0% | 0% | 4875.0488 | 0 | 0 | 4847504.7527 | 0 | 0 | 585.0059 | 0 | 0 | 1706267.0724 | 0 | 0 | 0.4 | 1950.0195 | 195001.9511
| 7.5 | 24.29% | 19500.1951 | 138500135.7924 | 122851.2292 | 20% | 5% | 0% | 3900.039 | 975.0098 | 0 | 5817005.7033 | 277000.2716 | 0 | 702.007 | 438.7544 | 0 | 1365013.6579 | 390003.9023 | 0 | 0.4 | 1560.0156 | 156001.5609
| 10 | 12.15% | 9750.0976 | 92333423.8616 | 81900.8195 | 20% | 10% | 2% | 1950.0195 | 390.0039 | 195.002 | 3878003.8022 | 369333.6954 | 277000.2716 | 468.0047 | 234.0023 | 234.0023 | 682506.829 | 156001.5609 | 234002.3414 | 0.4 | 780.0078 | 78000.7805
| 15 | 10.53% | 8450.0845 | 120033451.0201 | 106471.0653 | 20% | 15% | 5% | 1690.0169 | 1267.5127 | 422.5042 | 5041404.9428 | 720200.7061 | 900250.8827 | 608.4061 | 1140.7614 | 760.5076 | 591505.9184 | 507005.0729 | 507005.0729 | 0.4 | 676.0068 | 67600.6764
| 20 | 4.049% | 3250.0325 | 61555615.9077 | 54600.5463 | 20% | 15% | 5% | 650.0065 | 487.5049 | 162.5016 | 2585335.8681 | 369333.6954 | 461667.1193 | 312.0031 | 585.0059 | 390.0039 | 227502.2763 | 195001.9511 | 195001.9511 | 0.4 | 260.0026 | 26000.2602
| 25 | 2.429% | 1950.0195 | 46166711.9308 | 40950.4097 | 20% | 15% | 5% | 390.0039 | 292.5029 | 97.501 | 1939001.9011 | 277000.2716 | 346250.3395 | 234.0023 | 438.7544 | 292.5029 | 136501.3658 | 117001.1707 | 117001.1707 | 0.4 | 156.0016 | 15600.1561
| Total | 100% | 80275.8032 | 623250611.0659 | 552830.5315 |  |  |  | 16055.1606 | 3412.5341 | 877.5088 | 26176525.6648 | 2012868.6402 | 1985168.613 | 3159.0316 | 2837.2784 | 1677.0168 | 5619306.2252 | 1365013.6579 | 1053010.5361 |  | 6422.0643 | 642206.4257
[9 empty] | 20% | 4.251% | 1.093% |  |  | 30174562.918 |  |  | 7673.3268
[13 empty] | After NTG | 24139650.3344
Verification of Savings (reverse engineering results) |  | Total Tonnage In Toronto | 460692.1096 | T
|  | Assumed Fan RunTime | 78 | Hrs/Wk
|  | Compressor RunTime | 600 | Hrs/Yr | Calculated in CE Tool
| T'Stat Savings | #Participants | 16055.1606 | Units
|  | Participating Tonnage | 131626.317 | T
|  | Average Tonnage | 8.1984 | Tavg
|  | Average Fan bHP | 2.0496 | HP-avg
|  | Average Fan kW | 1.529 | kW-avg
|  | Estimated T'Stat Savings | 1630.4119 | kWh | Conservatively assumes only savings are from fan
|  | Runtime Savings | 1066.3271 | Hrs/Year
|  | Weekly Runtime Savings | 20.5063 | Hrs/Wk
|  | Daily Runtime Savings | 2.9295 | Hrs/d
|  | New Operating Hours | 57.4937 | Hrs/Wk
| OCC Sensor Savings | #Participants | 3412.5341 | Units |  |  |  |  | 0
|  | Participating Tonnage | 47287.9731 | T |  |  |  |  | 0
|  | Average Tonnage | 13.8571 | Tavg |  |  |  |  | 7312.5732
|  | Average Fan bHP | 3.4643 | HP-avg |  |  |  |  | 3900.039
|  | Average Fan kW | 2.5844 | kW-avg |  |  |  |  | 19012.6902
9750.0976
|  | Estimated OCC Savings | 589.8457 | kWh | Conservatively assumes only savings are from fan |  |  |  | 7312.5732
|  | Runtime Savings | 228.2369 | Hrs/Year
|  | Weekly Runtime Savings | 4.3892 | Hrs/Wk
|  | Daily Runtime Savings | 0.62702 | Hrs/d
|  | New Operating Hours | 53.1045 | Hrs/Wk
| OCC Sensor Savings | #Participants | 877.5088 | Units |  |  |  |  | 0
|  | Participating Tonnage | 13975.1398 | T |  |  |  |  | 0
|  | Average Tonnage | 15.9259 | Tavg |  |  |  |  | 0
|  | Average compresson energy | 19.1111 | kW-avg |  |  |  |  | 1950.0195
6337.5634
|  | Estimated OCC Savings | 2262.2778 | kWh | Conservatively assument no incremental fan savings |  |  |  | 3250.0325
|  | Runtime Savings | 118.375 | Hrs/Year |  |  |  |  | 2437.5244
|  | Overall Cooling Savings | 19.73%

## 8. Energy Efficient Measures
8 | Energy Efficient Measures
| Review Criteria |  | IESO Staff to complete this box
Section Approved? (Yes/No):
Yes/No
Is all measure information fully complete in this section (matches CE Tool)?
Is the quantity of projected measures reasonable compared to the projected number of program/pilot participants? (Based on results from Ontario or similar jurisdictions and/or primary market research)
Are Participant Incentives reasonable and substantiated? (Based on results from Ontario or similar jurisdictions and/or primary market research)
Section 8: LDC Questions (please complete all grey sections below)
This section will allow the IESO to substantiate all inputs in the cost effectiveness tool. Please base on your inputs in the CE tool. (CE TOOL = Cost Effectiveness Tool in LDC Tool Kit -http://www.ieso.ca/Pages/Conservation/Conservation-First-Framework/LDC-Tool-Kit.aspx)
Important Note: The list of Eligible Measures below should include all: widgets, audits, energy assessments, energy reports, operations and maintenance, etc.
1a | Please complete the table below by including projected totals for all eligible measures included in the proposed program or pilot (add rows as necessary). Please substantiate projections (with sources):
The measures in column D are eligible for installation under this Program or Pilot (a program rule)
| List of Eligible Measures ("Column C + D"): |  |  | Quantity of projected measures per project | Justification/Data Sources1
| 1 | web enabled smart thermostat |  | 16055.1606 | 20% of market as previously noted
| 2 | addition of occupancy sensor control |  | 3412.5341 | 20% of Participants
| 3 | addition of demand controlled ventilation system |  | 877.5088 | 15% of larger units
| 4 |  |  |  | see RTU Assumptions Worksheet for details
1 If further detail is needed to substantiate the total projected # of measures in this program or pilot, please use the space below:
1b | Please describe any additional Project eligibility requirements beyond the list of measures included in 1a: (Project Eligibility Requirement: The Project must be at a Distribution Connected Facility) (a program rule)
2 | Please complete the table below to document and substantiate the Participant Incentives for your proposed program per measure:
| Eligible Measures: |  |  | Participant Incentive (Per Unit) (a program rule) | Please list all information sources, market research1 and assumptions made to arrive at the Participant Incentives
| 1 | web enabled smart thermostat |  | 350 | Maximum anticipated cost of assessment and Smart Thermostat (market pricing)
| 2 | addition of occupancy sensor control |  | 400 | maximum incremental upgrade cost rebated for installation of occupancy sensors. (estimate of labour and material for 4,000ft2 of space)
| 3 | addition of demand controlled ventilation system |  | 1200 | maximum incremental upgrade cost rebated for installation of CO2 sensors and fan controller.
4
1 If market research was conducted to design Participant Incentives, please include who conducted the research, the methodology, sample size and key findings
3 | Please complete the table below by listing all measures included in the proposed program or pilot (add rows as necessary):
[Add an 'x' next to each measure to indicate if it is a prescriptive or custom measure. If you have made any changes in the Cost Effectiveness tool to prescriptive measures, they MUST be considered custom and listed as such.]
| Eligible Measures: |  |  | Prescriptive Measure selected from the "Measures" tab in the CE Tool |  | Custom Measure created for this program/pilot in the "Custom Measure Input" tab of the CE Tool
| 1 | web enabled smart thermostat |  |  |  | x
| 2 | addition of occupancy sensor control |  |  |  | x
| 3 | addition of demand controlled ventilation system |  |  |  | x
4
To be conservative, the occupancy sensor upgrades were set to 20% of Participants as some locations will not be well suited to the installation of occupancy control. The DCV participants reflect market whose outdoor air requirements are higher than average (e.g.. restaurants).
Ultimately all of the measures are cost effective therefore an increase in the quantities of any of the measures will not adversely affect the overall positive cost-effectiveness results.
Project must undertake a rooftop assessment provided free of charge to the customer by the Toronto Hydro contractor [NTD: Assessment costs for Participants who don't proceed with repairs are accounted for in the Program Admin Budget "Other Program Costs"].
Participant must effect repair to the rooftop unit prior to receiving the Measures and incentives.
Eligible equipment includes all packaged HVAC, such as a roof top unit, which has a minimum of 4 tons of air conditioning compressors.
Repairs to the Eligible equipment may be completed by the LDC contractor or the Customers contractor at the customer's choice.
Exception to these Rules granted for a new roof top unit is being installed (i.e. mid-stream option). [NTD: Budgets conservatively assume all Participants are direct as mid-stream will be offered at a much lower cost].

## 8a. EE Measures - Custom
8a | EE Measures - Custom
| Review Criteria |  | IESO Staff to complete this box
Section Approved? (Yes/No):
Yes/No
Is all custom measure information fully complete in this section (matches CE Tool)?
Are custom measure assumptions fully substantiated? (based on independent 3rd party evaluation, measurement and verification results from similar jurisdictions or other independently funded and statistically significant verified results)
| Are custom measure assumptions reasonable? (based on similar jurisdictions and/or primary market research) |  |  |  |  | -->Please provide question references from the questionnaire below to indicate which assumptions are NOT reasonable:
Section 8a: LDC Questions (please complete all grey sections below)
This section will allow the IESO to substantiate all inputs in the cost effectiveness tool. Please complete based on your inputs in the CE tool. (CE TOOL = Cost Effectiveness Tool in LDC Tool Kit -http://www.ieso.ca/Pages/Conservation/Conservation-First-Framework/LDC-Tool-Kit.aspx)
The following questions apply only to custom measures identified in previous tab:
Please include 1 custom measure per line below (you may not need all 8 rows). If needed, please add additional rows.
Custom Measures Section
1 | Annual Operating Hours: Please indicate below the load profile selected for each custom measure with a justification for this choice.
| Custom Measures: |  |  | Annual Operating Hours |  |  | Justification
| 1 | web enabled smart thermostat |  | 4056 |  |  | 78 hrs/week was selected as lowest of typical small office; restaurant, retail store or small factory. Facilities with higher run times will see higher savings.
| 2 | addition of occupancy sensor control |  | 4056
| 3 | addition of demand controlled ventilation system |  | 4056
4
2 | Load Profile: Please indicate below the annual operating hours for each custom measure with a justification for this choice.
| Custom Measures: |  |  | Load Profile |  |  | Justification
| 1 | web enabled smart thermostat |  | PSP-Business-Commercial-Space_Cooling_&_Heating |  |  | sole purpose of unit is for space conditioning
| 2 | addition of occupancy sensor control |  | PSP-Business-Commercial-Space_Cooling_&_Heating |  |  | sole purpose of unit is for space conditioning
| 3 | addition of demand controlled ventilation system |  | PSP-Business-Commercial-Space_Cooling_&_Heating |  |  | sole purpose of unit is for space conditioning
4
Base Case Questions:
3 | Base Case Description: Provide a complete description of the base case measure in the table below. Including: what the measure is, what the measure does and the intended use of the measure (should also include any size or performance restrictions; i.e. "Omni-directional LED A Lamp ≤12W and ≥1100 Lumens")
| Custom Measures: |  |  | Base Case Complete Description:
| 1 | web enabled smart thermostat |  | Functional roof top unit of varying sizes 4T and higher. Fan operates continuously during occupied hours (with buffer before and after hours) and when a call for heat/cool in unoccupied hours. Heating and Cooling controlled by manual thermostat with drifting and hunting.
| 2 | addition of occupancy sensor control
| 3 | addition of demand controlled ventilation system
4
4 | Base Case Energy Consumption: Provide the energy consumption and demand for the base case measure in the table below. Please substantiate (with sources).
| Custom Measures: |  |  | Base Case (kWh/Ton) | Base Case (kW/Ton) | Please indicate sources and method used to arrive at these numbers
| 1 | New Roof Top Unit |  | 947 | 1.2 | Based on efficient new roof-top unit >4T
| 2 |  |  |  |  | Average new roof top unit operates at >1kW/T based on most manufacturers data sheets (e.g.. Carrier weathermaster).
| 3 |  |  |  |  | Fans at low static pressure are typically sized 0.25bHP/Ton (.2kW/T) per manufactures data sheets (e.g.. Carrier Weathermaster)
4
5 | Base Case Measure Full Installed Cost: Provide the full installed cost for the base case measure in the table below. Please substantiate (with sources).
| Custom Measures: |  |  | Full Installed Cost ($) |  | Please indicate sources used to determine cost
| 1 | n/a
| 2 | n/a
| 3 | n/a
| 4 | n/a
Conservation Case Questions (Energy Efficient Measure):
6 | Energy Efficient (EE) Measure Description: Provide a complete description of the energy efficient measure in the table below. Including: what the measure is, what the measure does and the intended use of the measure (should also include any size or performance restrictions; i.e. "Omni-directional LED A Lamp ≤12W and ≥1100 Lumens")
| Custom Measures: |  |  | Energy Efficient Measure Complete Description:
| 1 | web enabled smart thermostat |  | Smart thermostat provides better control of roof top unit to actual operating hours and precise temperature control. Run time hours will be reduced on the fan and cooling temperature will be more efficiently control. Only web enabled smart thermostats approved by the LDC are eligible - allowing customer remotely add overtime hours when needed (vs. pre-programmed)
| 2 | addition of occupancy sensor control |  | Occupancy sensor add on - integrated into the thermostat or as a control input to the thermostat controller provides precise control of the roof top unit. This allows for the space temperature to be set-up or set-back when the facility is unoccupied during normal working hours (e.g. lunch break in an office).
| 3 | addition of demand controlled ventilation system |  | Added to the Smart Thermostat, CO2 control of ventilation (i.e. outside air) into the space allows for the roof top unit to be controlled in the most efficient manner. Addition of economizer control and variable speed fan (vsd, ecm or 2-speed) will dramatically reduce energy consumption. Target market are units >7T (consistent with ASHRAE advanced RTU study)
4
7 | Energy Efficient (EE) Effective Useful Life (EUL): Provide the EUL for the custom EE measure in the table below. Please substantiate (with sources).
| Custom Measures: |  |  | EUL (years) |  | Please indicate sources and method used to arrive at the EUL
| 1 | web enabled smart thermostat |  | 15 |  | generally accepted life expectancy of thermostat
| 2 | addition of occupancy sensor control |  | 15 |  | generally accepted life expectancy of sensors
| 3 | addition of demand controlled ventilation system |  | 15 |  | generally accepted life expectancy of primary equipment
4
8 | Energy Efficient (EE) Measure Consumption: Provide the energy consumption and demand for the custom EE measure in the table below. Please substantiate (with sources).
| Custom Measures: |  |  | EE Measure (kWh) | EE Measure (kW) | Please indicate sources and method used to arrive at these numbers
| 1 | web enabled smart thermostat |  | 1630.4119 | 0.48586 | Engineering Calculations based on mix of RTU units and fan sizes. Savings are 2% cooling and 9 hours/wk of fan runtime reduction due to more precise controller.
| 2 | addition of occupancy sensor control |  | 589.8457 | 0.17577 | Incremental savings based on Engineering Calculation for additional set-up of temperatures offered by more precise control. 3% more cooling savings and 3 more hours per week of fan runtime savings.
| 3 | addition of demand controlled ventilation system |  | 2262.2778 | 0.67416 | Incremental savings based on Engineering Calculation for appropriate space ventilation. Conservative 18% average speed reduction in fan system as well as the associated cooling savings. Applicable to larger RTU.
4
9 | Energy Efficient (EE) Measure Gas and Water Savings (if applicable): Provide the gas and water savings (consumption and demand) for the custom EE measure in the table below. Please substantiate (with sources).
| Custom Measures: |  |  | Gas savings (MMBtu) | Water savings (Litres) | Please indicate sources and method used to arrive at these numbers
| 1 | web enabled smart thermostat |  | 0 | 0 | No gas savings attributed to program to enable Enbridge to add-on - avoids double counting savings between utilities
| 2 | addition of occupancy sensor control |  | 0 | 0
| 3 | addition of demand controlled ventilation system |  | 0 | 0
4
10 | Energy Efficient (EE) Net-To-Gross (NTG): Provide the Net-to-gross ratios (consumption and demand) for the custom EE measure in the table below. Please substantiate (with sources).
| Custom Measures: |  |  | NTG Energy (0.00) | NTG Demand (0.00) | Please indicate sources and method used to arrive at these ratios
| 1 | web enabled smart thermostat |  | 0.8 | 0.8 | Estimate based on slight improvement from Retrofit Program NTG - higher degree of LDC influence on new programs
| 2 | addition of occupancy sensor control |  | 0.8 | 0.8
| 3 | addition of demand controlled ventilation system |  | 0.8 | 0.8
4
11 | Energy Efficient (EE) Measure Costs: Provide the EE full installed cost for the custom EE measure in the table below. Please substantiate (with sources).
| Custom Measures: |  |  | EE Full Installed Cost ($) |  | Please indicate sources used to determine cost
| 1 | web enabled smart thermostat |  | 350 |  | Maximum anticipated cost of assessment and Smart Thermostat (market pricing)
| 2 | addition of occupancy sensor control |  | 550 |  | maximum incremental upgrade cost rebated for installation of occupancy sensors. (estimate of labour and material for 4,000ft2 of space)
| 3 | addition of demand controlled ventilation system |  | 2600 |  | Incremental cost based on gridsaver and advanced rooftop control pilots
4
Note on F89: andrew pride: Calculations provided by CE Tool for selected load profile

## 9. Budget
9 | Budget
| Review Criteria |  | IESO Staff to complete this box
Section Approved? (Yes/No):
Yes/No
Is the budget complete (matches CE tool)?
Are costs included in the budget reasonable and substantiated? (based on historic costs, costs in similar jurisdictions, quotes and/or competitive procurements)
Are all ineligible program costs outlined?
Are costs included in the P4P cost table reasonable and substantiated? (based on historic costs, costs in similar jurisdictions, quotes and/or competitive procurements)
Section 9: LDC Questions (please complete all grey sections below)
1 | Please complete the budget table below based on the inputs for this program/pilot in the Cost Effectiveness Tool:
|  |  |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2016-2020
| Participant Incentives |  |  |  | 1607466.08 | 2411199.13 | 2009332.6 | 2009332.6 | 8037330.41 |  |  | Budget Result Summary
| LDC labour |  | Fixed |  | 120000 | 120000 | 120000 | 120000 | 480000 |  |  |  |  | PROGRAM YEAR
|  |  | Variable | [10 empty] | 2017 | 2017 | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2020 | 2020
| Third Party Costs |  | Fixed |  | 73000 | 75000 | 77000 | 77000 | 302000 |  |  | SECTOR | PROGRAM | Incentives | Program Admin | LDC Variable Costs | Central Service Costs | 2017 Sub-Total | Incentives | Program Admin | LDC Variable Costs | Central Service Costs | 2018 Sub-Total | Incentives | Program Admin | LDC Variable Costs | Central Service Costs | 2019 Sub-Total | Incentives | Program Admin | LDC Variable Costs | Central Service Costs | 2020 Sub-Total | Total
|  |  | Variable |  | 0 |  |  |  | 0 |  |  | Non-Residential | Smart RT | 1607466.08 | 471441.29 | 0 | 0 | 0 | 2411199.13 | 487661.93 | 0 | 0 | 0 | 2009332.6 | 407551.61 | 0 | 0 | 2078907.37 | 2009332.6 | 377551.61 | 0 | 0 | 2898861.06 | 2488884.215
| Marketing Spend |  | Fixed |  | 150000 | 100000 | 50000 | 20000 | 320000 |  |  | Total |  | 1607466.08 | 471441.29 | 0 | 0 | 0 | 2411199.13 | 487661.93 | 0 | 0 | 0 | 2009332.6 | 407551.61 | 0 | 0 | 2078907.37 | 2009332.6 | 377551.61 | 0 | 0 | 2898861.06 | 2488884.215
Variable
| Central Services Cost (province-wide/ local/regional only) (a program rule) |  | Fixed
|  |  | Variable | [9 empty] | PROGRAM YEAR
| Other Program Costs |  | Fixed |  | 128441.29 | 192661.93 | 160551.61 | 160551.61 | 642206.44 |  |  |  | 2017 | 2017 | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2020 | 2020
|  |  | Variable | [8 empty] | PROGRAM | LDC Labour | Third Party Costs | Marketing Spend | Other Program Costs | 2017 Sub-Total | LDC Labour | Third Party Costs | Marketing Spend | Other Program Costs | 2018 Sub-Total | LDC Labour | Third Party Costs | Marketing Spend | Other Program Costs | 2019 Sub-Total | LDC Labour | Third Party Costs | Marketing Spend | Other Program Costs | 2020 Sub-Total | Total
| Total (2016-2020) |  | Fixed |  | 471441.29 | 487661.93 | 407551.61 | 377551.61 | 1744206.44 |  |  | Smart RT | 120000 | 73000 | 150000 | 128441.29 | 959103.22 | 120000 | 75000 | 100000 | 192661.93 | 2121758.05 | 120000 | 77000 | 50000 | 160551.61 | 343000 | 120000 | 77000 | 20000 | 160551.61 | 1254103.22 | 2703309.66
|  |  | Variable |  | 1607466.08 | 2411199.13 | 2009332.6 | 2009332.6 | 8037330.41 |  |  |  | 120000 | 73000 | 150000 | 128441.29 | 959103.22 | 120000 | 75000 | 100000 | 192661.93 | 2121758.05 | 120000 | 77000 | 50000 | 160551.61 | 343000 | 120000 | 77000 | 20000 | 160551.61 | 1254103.22 | 2703309.66
|  |  | Total |  | 2078907.37 | 2898861.06 | 2416884.21 | 2386884.21 | 9781536.85 | 9781536.8592 | CE Check ok
2 | Please explain below how you arrived at the costs above by completing the table below:
Please provide cost justifications below (i.e. quoted costs, any calculations, competitively procured?, etc.)
| Participant Incentives |  |  | Market pricing
| LDC labour |  |  | Toronto Hydro estimate of time.
| Third party costs |  |  | 4% for measurement and verification
| Marketing Spend |  |  | Toronto Hydro estimate of expected marketing spend.
| Central Services Cost |  |  | None needed
| Other Program Costs |  |  | Estimate of $100 per assessment for customers who do not proceed to repair rooftop unity. Assumes 40% of customer will not proceed (excessively high to ensure budget is sufficient).
2a | Please describe below any ineligible costs associated with this program or pilot1: (a program rule)
1 Examples of ineligible costs in Retrofit: costs of the Participant’s labour, service, administration or overhead that are not incurred by a third party; financing costs; insurance costs; costs associated with post-installation work related to equipment maintenance or repair (unless this is a benefit of the program or pilot and included in cost effectiveness calculations); costs of spare parts, spare equipment or other inventories; costs of purchase or lease of tools for equipment installation; HST; and any costs already covered by funding or grants from the energy ratepayers or taxpayers in the Province of Ontario, (unless funding principally directed to Social Housing Providers and if such funding, when combined with the Participant Incentive, does not exceed the Project cost) or rebates from manufacturers, wholesalers or other supply chain participants.
Please refer to the Conservation First (2015-2020) toolkit for the Pay-for-Performance Rules:
3 | [Pay for Performance only] Please indicate below which Pay for Performance Option you have selected by adding an "x" in one grey box: (a program rule)
Option 1
Option 2
Option 3
3a | [Pay for Performance only] Please complete the table below to outline the Pay-for-Performance Rate breakdown for this proposed program/pilot: (a program rule - P4P rate only)
Totals
Rate/kWh
Components:
Administration Financing Cost
Administration Tax or Payments in Lieu
Participant Incentives paid (for P4P)
Incentives from IESO (P4P Revenue)
Participants who upgrade their Eligible equipment outside of this Program may apply through Retrofit Program.
Required operational repairs to the Equipment are not Eligible costs.

## 10. Cost Effectiveness
10 | Cost Effectiveness
| Review Criteria | IESO Staff to complete this box
Section Approved? (Yes/No/NA):
IESO Review Note: If a pilot is not cost-effective, please add "NA" below
Yes/No/NA
Is the program/pilot cost effective? (TRC & PAC > 1.0)
Section 10: LDC Questions (please complete all grey sections below)
1 | [ATTACHMENT REQUIRED] Please attach the completed Cost Effectiveness Tool excel spreadsheet used to arrive at cost effectiveness results in "Section 3: Summary Sheet"
CE TOOL ATTACHED
2 | [Innovation Fund pilots only] If the proposed pilot has a TRC and/or PAC < 1.0, please demonstrate below how the pilot can become cost-effective on a larger scale:
Notes:
The Minister’s Direction of March 31, 2014 includes a requirement that the IESO ensure “there is a positive benefit-cost analysis of each... Local Distributor CDM Program utilizing the IESO’s Total Resource Cost Test (TRC) and the Program Administrator Cost Test found in the IESO Cost-Effectiveness Guide.

## 11. Risk Analysis
11 | Risk Analysis (SKIP SECTION for Pay for Performance Programs/Pilots)
| Review Criteria |  | IESO Staff to complete this box
Section Approved? (Yes/No):
Yes/No
Are all major risks identified & accompanied by a mitigation strategy?
Section 11: LDC Questions (please complete all grey sections below)
1 | What are the factors that could make your program unsuccessful or not cost effective and what is your strategy to deal with these risk factors? Please complete the risk analysis table below (please add rows if necessary, include "NA" if risk doesn’t apply to this program or pilot):
| Risk Factor: | Description of the Risk |  | Mitigation Strategy
| Number of participants | Participation levels drop below 6,400 (point at which CE is 1.0) |  | Tracking ongoing participation levels - if less than 50% of forecast (tracking to 8,000 units), reduce overhead spend or renegotiate delivery contract to mitigate cost.
| Gross Energy Savings | Average runtime of packaged units is significantly less than business case assumption. |  | Increase eligibility to higher tonnage units - will result in higher per unit savings (as equipment consumes proportionately higher energy)
| Fixed Costs | Costs increase beyond budget. |  | Toronto Hydro directly manages these costs.
| Variable Costs | Assessment not delivering anticipated Participation levels. |  | Contractor to be on performance management plan. Ultimately Toronto Hydro would prefer to have contractor assume all risk for assessments.
| Net-to-gross ratio | EM&V contractor discovers a high percentage of free riders |  | Unlikely to happen for this new program. CE is >3.0 so there is significant room for change to NTG
| Life Expectancy of Equipment | Equipment chronically fails prematurely |  | Program is still cost effective at a 4 year life expectancy. Warranty is typically 3 years for theses products.
[Other - replace with description]
[Other - replace with description]

## 12. Measurement & Verification
12 | Measurement & Verification
| Review Criteria |  | IESO Staff to complete this box
Section Approved? (Yes/No):
Yes/No
Can this program/pilot be evaluated based on the design and data collection plan?
Will the QA/QC plan allow for complete IESO compliance checks?
This section will allow IESO to create an evaluation methodology based on your program design and the information below (data collection plan, measuring the base line and energy efficient case) NOTE: a pre-consultation with IESO EM&V (by request) before designing your program is highly recommended.
Please refer to the Conservation First (2015-2020) toolkit for evaluation and measurement & verification guidelines:
http://www.ieso.ca/Pages/Conservation/Conservation-First-Framework/LDC-Tool-Kit.aspx
Section 12: LDC Questions (please complete all grey sections below) (entire tab is a program rule)
1 | Please choose one of the options in the table below indicating the Measurement & Verification approach for the proposed program or pilot: (if you are unsure of the appropriate evaluation approach to choose, please complete the IESO pre-consultation form to consult with IESO EM&V).
| Check if applicable | Approach |  |  |  | Include rationale for choosing approach
| x | Deemed Savings - uses savings values for program-supported measures with well-known and documented savings values. |  |  |  | Assessor needs to visit every site and can generate the savings from pre-established engineering calculations.
Large-Scale Data Analysis - applies a variety of statistical methods to measured facility energy consumption meter data (almost always whole-facility utility meter billing data) and independent variable data to estimate gross energy and demand impacts.
| x | Custom M&V - is used when there is high uncertainty and or variability in the potential savings and it requires that gross savings be tracked and estimated on a project-by-project basis. |  |  |  | for DCV only
2 | If the proposed program or pilot includes custom measures, please explain below how the baseline will be measured for each custom measure:
Custom Measures: |  |  |  | How will the baseline be measured for each custom measure?
1 | web enabled smart thermostat |  |  | Assessor will be equipped with data gathering device to collect pertinent M&V information for baseline and as operated. Data to be collected will included at a minimum, runtime hours (before and after), fan HP (or bHP), qty of compressors; total compressor input (Tonnes or MMBtu); conditioned space area and use.
2 | addition of occupancy sensor control |  |  | Additional data collection to include qty of sensors; min on time setting; anticipated vacancy rate during unoccupied periods.
3 | addition of demand controlled ventilation system |  |  | Historical energy data will be collected. Data for a period of 12 months following retrofit will be collected through the Smart web enabled thermostat to verify actual energy savings.
4
3a | To ensure that each evaluation produces verified net program savings that comply with the statistical rigor outlined in the EM&V protocols, the LDCs, the IESO and their agents must ensure that adequate data is collected and transmitted to the IESO in a timely and consistent manner. The minimum reporting requirements for any program are embodied in the Data and Reporting Requirements Rules.
http://www.powerauthority.on.ca/sites/default/files/conservation/Data%20and%20Reporting%20Requirement%20Rules%20Final%20v1_10312014.pdf
The LDC will meet the minimum reporting requirements for any program will be available to the IESO for evaluation purposes: (a program rule)
| Yes | x
| No |  | (See below -->)
3b | If no, please state the reasons why: (a program rule)
3c | Please indicate any challenges that you may encounter in providing the required data to the IESO for evaluation purposes:
4 | Please complete the Quality Assurance and Quality Control table below. The LDC will collect the following items to ensure they are in place for potential compliance checks: (a program rule)
| Requirements to consider (as applicable): | [5 empty] | Yes/No/NA
| Participant Incentives paid in accordance to program rules | [5 empty] | Yes
| Program Eligibility Criteria has been met | [5 empty] | Yes
| Participant Eligibility has been met | [5 empty] | Yes
| Facility Eligibility has been met | [5 empty] | Yes
| Project and Measures eligibility met | [5 empty] | Yes
| Signed Work Order/Participant Agreements | [5 empty] | Yes
| Existing Equipment at the Facility verified by means of photo evidence | [5 empty] | NA
| Eligible cost criteria met | [5 empty] | NA
| Record Keeping and Data Submission Requirements met | [5 empty] | Yes
| Invoicing requirements met | [5 empty] | NA
| Equipment replaced is disposed of or decommissioned (certificate) as required | [5 empty] | NA
[INSERT Other as required]
5 | The LDC agrees that it will be bound by the Measurement and Verification Plan and QA/QC requirements produced by the IESO based on this section 12 (Measurement & Verification)
No challenges anticipated.

## 16. Participant Agreement
16 | Participant Agreement (ONLY if additional terms are necessary beyond ECA)
| Review Criteria | IESO Staff to complete this box
Section Approved? (Yes/No/NA):
"NA" if not a pilot
Yes/No/NA
Are additional participant agreement terms included below (not covered in ECA) if the program/pilot requires additional terms?
Section 16: LDC Questions (please complete all grey sections below)
1 | Please include below any additional participant agreement terms not covered in the Energy Conservation Agreement (ECA): (a program rule)
(The design of certain programs may require additional terms. For example, opt-out social benchmarking pilots required additional privacy terms in participant agreements. If you are unsure if this program/pilot requires additional terms and would like assistance from the IESO, please complete the pre-consultation form.)
1. Participant agrees Toronto Hydro, or its agent, may freely access data from the smart thermostat for the purposes of collecting energy savings data for its internal purposes and for its performance reporting to the IESO and regulators.

## 13. Program Rules
13 | Program Rules (Province-wide Programs ONLY)
| Review Criteria | IESO Staff to complete this box
Section Approved? (Yes/No/NA):
"NA" if not a province-wide program
Yes/No/NA
Are new/amended (w. black line) program rules included?
Are the new/amended program rules comprehensive?
Section 13: LDC Questions (please complete all grey sections below)
1 | [ATTACHMENT REQUIRED] Please attach a Word document that includes program rules for this proposed province-wide program OR a Word document copy of the current program rules with tracked changes (black line version) for a change to an existing province-wide program. WORD versions of program rules are available from the IESO upon request.
For province-wide program rules, please pre-consult with IESO legal (form in the Tool Kit) to ensure that all parties are in agreement with rule changes.
PROGRAM RULES ATTACHED

## 14. Value-Added Central Service
14 | Value-Added Central Services and Province-wide Central Services (Province-wide/Regional/Local Programs)
| Review Criteria | IESO Staff to complete this box
Section Approved? (Yes/No/NA):
"NA" if province-wide central services and/or value-added central services not requested
Yes/No/NA
Is the information below regarding province-wide central services and/or value-added central services complete?
Are the Gantt Chart and Statement of Work attached and complete?
Are the timelines included in the Gantt Chart reasonable (i.e. enough lead time to deploy additional province-wide or value-added central services)
Section 14: LDC Questions (please complete all grey sections below)
1 | Please complete the table below to indicate whether the proposed program (or program change) requires new or changes to province-wide central services and/or value-added central services: (Add "NA" if services are not needed)
|  |  | Describe what is needed… |  | Proposed Budget (a program rule)
Program Delivery Services
Fulfillment Services
Technical Support Services1
IESO Call centre
Capability Building/Training Services
Market Research
Marketing
[Other - replace with description]
[Other - replace with description]
[Other - replace with description]
[Other - replace with description]
1 i.e. technical reviews, vendor developed tools, etc.
If the proposed program requires province-wide central services and/or value-added central services, please:
2 | [ATTACHMENT REQUIRED - Appendix A] Please attach a completed copy of the Activity Timeline (Gantt Chart) for the province-wide central services and/or value-added central services you have requested:
WORK BACK STRUCTURE ATTACHED
3 | [ATTACHMENT REQUIRED - Appendix B] Please attach a completed copy of the Scope of Work for the Value-Added Central Services you have requested:
SCOPE OF WORK ATTACHED
Notes:
If requested by LDCs, the IESO may procure and administer program delivery services on behalf of, and in participation with the LDC(s) where such an approach would result in cost efficiencies for CDM programs. Any value added services procured on behalf of LDCs that are directly related to the delivery of a program will be allocated to the LDCs as part of their CDM Plan. For example, value added services may include procured services such as fulfillment and/or delivery agent administration for the retailer coupon program and the residential HVAC program. The IESO commits that any value added services allocated to LDCs will be cost effective, as measured by the program administrator cost (PAC) test.

## 15. Project Milestones
15 | Project Milestones (LDC Innovation Fund Pilots ONLY)
| Review Criteria |  | IESO Staff to complete this box
Section Approved? (Yes/No/NA):
"NA" if not a pilot
Yes/No/NA
Is the milestone chart complete?
Section 15: LDC Questions (please complete all grey sections below)
1 | Please complete the chart below (see below for details on the reports)
| Reports | Milestones (Describe below all milestones leading up to the mid-point and final reports - add/remove rows as necessary) | Delivery Date (Can be dates or weeks after contribution agreement is executed)
Mid-point Report
Final Report
Reconciliation Report
Midpoint Report (which should contain the following)
1. Deliverables for included Milestones
2. Eligible Expense budget update and Expenditures to date.
3. An update on the progress of all activities set out in Pilot Work Plan and Milestones of the Pilot Proposal.
4. A description of any Pilot Related Property procured, developed or created by the Recipient.
5. The Recipient's analysis (strengths, weaknesses, threats and opportunities of pilot design and delivery as implemented) of pilot design and delivery to date.
6. Other such information regarding the implementation of the Pilot that IESO may request.
The midpoint report should be submitted when approximately 50% of the work is completed for the pilot, and according to the timeline specified in the business case and executed contribution agreement.
Final Report (which should contain the following)
1. Deliverables for included Milestones
2. Eligible Expense budget update and Expenditures to date.
3. An update of the Project Schedule, including status of each activity listed in Section 18 Pilot Work Plan and Milestones of the Pilot Proposal.
4. A description of any Pilot Related Property procured, developed or created by the Recipient.
5. The Recipient's analysis (strengths, weaknesses, threats and opportunities of pilot design and delivery as implemented).
6. Other such information regarding the implementation of the Pilot that IESO may request.
The final report should be submitted when the work is completed for the pilot.
If timelines in the milestone chart above are changed, an Exception Report must be submitted to the IESO with new timelines outlined.
Reconciliation Report (should include the following table, which maps to the submitted budget in the business case, as updated in the final report.)
| Eligible Expense Category | Total Eligible Expense ($) | Total Eligible Expense Paid to Date ($) | Total Additional Eligible Expense Claimed Without HST ($) | Total Eligible Expense With HST, if applicable ($)
The IESO will review submitted Midpoint and Final Reports within 10 business days, provided there are not any extenuating circumstances.

## 17. Definitions
17 | Definitions: (NOT applicable to Province-Wide programs)
| Review Criteria | IESO Staff to complete this box
Section Approved? (Yes/No/NA):
"NA" if province-wide
Yes/No/NA
Are additional definitions defined below acceptable to IESO legal?
Section 17: LDC Questions (please complete all grey sections below)
1 | Please include below any additional definitions not already defined in this business case template. If you have changed a definition for this program or pilot from an already published definition in the Energy Conservation Agreement (ECA) or a set of Program Rules, please indicate the change below with reference to the original definition. (a program rule)

## 18. Available Resources
18 | Available Resources:
For Program Design:
| Source | Location | Description
1 | LDC Innovation Fund Approved Business Cases | (Extranet) LDC Innovation Pilots >> Documents >> Approved Business Cases | Location for all LDC Innovation Fund approved business cases.
2 | Local/Regional Program Business Cases | (Extranet) Conservation First 2015-2020 >> Documents >> Approved Local, Regional, Program Business Cases | Location for all approved local and regional program business cases.
3 | Program Rules - Province-Wide/Regional/Local | http://www.ieso.ca/Pages/Conservation/Conservation-First-Framework/Program-Rules.aspx | Program Rules for all approved province-wide/regional/local programs are saved here.
4 | IESO Market Research | (Extranet) Market Research >> Documents >> Save on Energy Customer Satisfaction | Location for saveONenergy customer satisfaction research results (quarterly)
5 | Conservation Fund - Summary of Pilot Projects | http://www.powerauthority.on.ca/sites/default/files/page/Conservation-Fund-Portfolio-May-2015.pdf | A summary of all Conservation Fund pilots. For further detail on a pilot, contact LDC.Support@ieso.ca
6 | E Source | https://www.esource.com/ | E Source is a resource made available to all LDCs. This is a good place to start for a jurisdiction scan of similar program offerings in North America. (Please do use caution when citing results from other jurisdictions to substantiate CE tool inputs in your business case. Make certain that the sample size in the evaluation is robust enough and that the jurisdiction is similar to Ontario economically and in terms of weather patterns.) If you are having trouble creating an E Source account, please contact, carolyn_doyle@esource.com
7 | Pay-for-Performance (P4P) Guideline | http://www.ieso.ca/Pages/Conservation/Conservation-First-Framework/LDC-Tool-Kit.aspx | There is a Pay-for-Performance guideline available is you are considering this funding mechanism for your program or pilot.
8 | Incentive Setting Guideline (coming soon) | http://www.ieso.ca/Pages/Conservation/Conservation-First-Framework/LDC-Tool-Kit.aspx | Coming soon! A document will soon be available to guide incentive setting for programs and pilots.
9 | ACEEE (American Council for an Energy-Efficient Economy) | http://aceee.org/ | ACEEE, NEEP and NEEA are great sources for technology information, program design and program evaluations from other jurisdictions. (Please do use caution when citing results from other jurisdictions to substantiate CE tool inputs in your business case. Make certain that the sample size in the evaluation is robust enough and that the jurisdiction is similar to Ontario economically and in terms of weather patterns.)
10 | NEEP (Northeast Energy Efficiency Partnerships) | http://www.neep.org/resources
11 | NEEA (The Northwest Energy Efficiency Alliance) | http://neea.org/resource-center
For Market Characterization:
| Source | Location | Description
12 | Stats Can - 2011 Census Data | https://www12.statcan.gc.ca/census-recensement/2011/dp-pd/index-eng.cfm | Stats Can is a good starting point when characterizing the market for a program or pilot
13 | MPAC data (Property profile by LDC territory) | (Extranet) Your LDC Folder >> Documents >> Market Research >> 2015 >> "MPAC2015_LDCName.xlsx" | MPAC Profiles: Individual reports available for each LDC territory profiling the properties in your territory. (if you have not executed a sub-license agreement, you will not see your report on the Extranet. Please contact LDC.Support@ieso.ca for access)
14 | Segmentation of Ontario Business Market | (Extranet) Conservation First 2015-2020>> Other Tools and Resources >> LDC Sales and Marketing >> LDC Sales Tools >> "IESO List of Ontario Businesses 2016 Update.xlsm" | The segmentation shows, for each sector and sub-sector, the number of locations and square footage as well as the extent of participation in Save on Energy programs.
15 | Greater Public Sector Buildings Database | https://www.ontario.ca/data/energy-use-and-greenhouse-gas-emissions-broader-public-sector | Shows the amount of energy used and greenhouse gases (GHG) emitted for the Broader Public Sector, i.e., municipalities, municipal service boards, school boards, universities, colleges and hospitals.
16 | OEB Yearbooks | http://www.ontarioenergyboard.ca/OEB/Industry/Rules+and+Requirements/Reporting+and+Record+Keeping+Requirements/Yearbook+of+Distributors | The Yearbooks of Electricity Distributors and Yearbooks of Natural Gas Distributors provide interested parties and the general public with financial and operational information collected from distributors. Information presented in the Yearbooks is compiled from data submitted through the Reporting and Record-Keeping Requirements (RRR).
17 | 2016 IESO Achievable Potential Study (coming soon) | (Extranet) Conservation First 2015-2020 >> Achievable Potential Study >> Documents | Coming soon!
For Savings Assumptions:
| Source | Location | Description
18 | IESO Measures & Assumptions List (MAL) | http://www.powerauthority.on.ca/opa-conservation/conservation-information-hub/evaluation-measurement-verification/measures-assumptions-lists | The IESO Prescriptive Measures and Assumptions List (“Prescriptive List”) is a collection of electricity conservation measures which present deemed energy and demand savings using prescriptive input assumptions (PIAs).
19 | IESO Program Evaluations | http://www.powerauthority.on.ca/opa-conservation/conservation-information-hub/evaluation-measurement-verification/reports | Location of evaluation reports conducted and prepared by independent third party evaluation contractors. The reports consist of programs evaluated by the EM&V group at the IESO. Most of these reports present energy and demand savings as well as recommendations for program improvements.
20 | Design Lights Consortium (DLC): Qualified Products List | https://www.designlights.org/QPL | Serves efficiency programs and the lighting industry by maintaining the leading public list of high quality, high efficiency LED products for the commercial sector.