Implementation of Ontario’s Fair Hydro Plan

Week of March 6, 2017

| Item | Key Deliverables / Considerations | Timing / Next Steps |
| --- | --- | --- |
| - Refinancing the Global Adjustment (ESP/IGS) |  |  |
| - ENERGY, LSB, IESO, OPG, OEB, TBS and MOF | - Legislation: - Defining mitigation and recovery mechanism; and - Establishing roles for IESO, OPG and OEB - Regulation (amend O.Reg.429/04) - Shareholder Declaration and Resolution - Third Party Technical Report re Long Lived Assets (TBD) - Accounting opinions from E&Y (OPG) and KPMG (IESO) - Financing: - IESO line of credit to bridge from May-July; - OEFC to OPG equity injection structure; and - OPG trust rating agency review and 3rd party lender market sounding (e.g., cost/term, etc) Considerations - GA refinancing legislation could also include legislative changes to enable broadening of RRRP, expanding of OESP and establishing of FN delivery credit. - Ongoing legal, accounting and financing risk assessments. - Impact on Electricity Sector Dedicated Income. - OEB-RPP Filing in May 2017. OEB may also be required to set new GA rate for RPP-eligible consumers. | - Report back to TBC/MBC by spring 2017, prior to going to LRC with any legislation, on the approach to refinance GA (per TBC/MBC Minute) - Report to TBC/MBC, LRC and Cabinet in spring 2017 (per Cabinet Minute) - Provide comfort level to allow OEB to include in May 2017 RPP - Summer 2017 implementation (June/July). OPG preference for July 1 to align with quarter-end |
| - Broadening Rural or Remote Rate Protection (RRRP) (SNAP) |  |  |
| - ENERGY, LSB and LDCs | - Legislation - Regulation (TBD) Considerations - Consideration of revising definitions of RRRP program for broadening to other LDCs and continue to have current structure in place to provide to existing consumers in Algoma and Remotes. - Technical/governance structures needed to flow taxpayer money to programs. Need to work with IESO/OEB/MOF. - Work with LDCs to consider any bill messaging. | - Report back to TB/MBC by Spring 2017 - Fall 2017 implementation (per Cabinet Minute) |
| - Expanding Ontario Electricity Support Program (OESP) (SNAP) |  |  |
| - ENERGY, LSB and OEB | - Legislation - Regulation (TBD) Considerations - Reach out to OEB to consider whether surplus funding of ~$100M could be used to increase OESP credits by 50%. Regulation can be updated quickly (need to consider whether posting on EBR is required). - Consider whether revised directive needed to continue having OEB administer program. - Legislation required to have program funded by taxpayers. - Technical/governance structures needed to flow taxpayer money to programs. Need to work with IESO/OEB/MOF. | - Report back to TB/MBC by Spring 2017 - Program in place in 2017 (per Cabinet Minute) |
| - Providing a First Nations On-Reserve Delivery Credit (SNAP) |  |  |
| - ENERGY and LSB | - Legislation - Regulation (TBD) Considerations - Work with LDCs on implementation details that need to be captured in legislation. - Legislation required to have program funded by taxpayers. - Technical/governance structures needed to flow taxpayer money to programs. Need to work with IESO/OEB/MOF. - Work with LDCs to consider any bill messaging. | - Report back to TB/MBC by Spring 2017 with final program details, including performance management framework, and clarifying how the programs aligns with the significant OEB estimate of program costs, from $13M to $20M - Program in place in 2017 (per Cabinet Minute) |
| - Establishing an Affordability Fund (CRED) |  |  |
| - ENERGY, IGS, LSB, TBS, MOF and H1 | - TBC/MBC Submission - Trust Structure - Transfer Payment Agreement (multi-party) Considerations - Legislative changes not required. - Funding needs to flow to the Trust prior to March 31, 2017. | Week of March 6, 2017: - TBC/MBC approval (March 6th) - CAB approval (March 8th) - Follow up calls with several LDCs and EDA to provide updates and outline proposed principles for the Fund ( Ongoing engagement with Hydro One, LSB, OPCD, CSD on principles and establishment of Trust and development of Transfer Payment Agreement (TPA) (including sharing of drafts for comment ); Week of March 13, 2017: - Hydro One to finalize establishment of Trust by March 17th - Continue development of TPA, including circulating near to final version by March 17th Week of March 20, 2017: - Execute TPA between the Ministry and the Trust by March 22nd - Initiate process to flow funds to the Trust; to be completed before March 31st April to May 2017: - Additional trustees to be appointment; Trust develops further details, e.g. customer eligibility criteria and processes for LDCs to apply for funds; to be developed in consultation with LDCs June 2017: - Report back to TB/MBC with final program details and a performance management framework including outcome measures and targets Summer 2017: - LDCs begin to apply to the Trust for funds |
| - Expanding ICI (ESP) |  |  |
| - ENERGY, LSB, IESO and LDCs | - Regulation (amend O.Reg.429/04) - Regulatory Registry (RR) posting Considerations - Amendments need to be in effect as much in advance of the consumer notification date to impact electricity bills this year (May 15, 2017). - RR posting is typically a minimum of 45-days for all regulatory changes affecting business to allow for review/comment. Note: RR posting is not a legal requirement but a best practice. - Working with the Ontario Chamber of Commerce on a targeted outreach campaign. | - RR posting on the proposed amendment - Report back to TBC/MBC by spring 2017 (per TBC/MBC Minute) - LRC [DATE] - Effective May 2017 (TBD) |
| - Energy Sector Efficiencies (i.e., Ontario Energy Board and IESO) (SNAP / ESP) |  |  |
| - ENERGY, LSB, OEB and IESO | OEB: - Directive / Letter (TBD) Considerations - Signal efficiencies intent in OEB business plan letter - Work with OEB/LDCs on LTEP document and proposed directive to OEB IESO: - Directive / Letter (TBD) Considerations - Opportunity to highlight Market Renewal in the next LTEP. - IESO’s stakeholder engagements on Market Renewal is ongoing. - Moving away from a two schedule system could impact consumer prices depending on implementation. - Most of the savings accrue from the move to a capacity auction. These savings do not materialize until the province has capacity requirements. | - Continue this work as part of LTEP |
| - Additional Initiatives for Small Business and Industrials (i.e., Class B) (ESP) |  |  |
| - ENERGY, MEDG, MOF, MOECC, MOL and Small Business | - Identify additional opportunities to assist Class B electricity consumers and small and medium sized manufacturers’ Considerations - TBD | - Report back to TBC/MBC and Cabinet in spring 2017 (per Cabinet Minute) |
| - Initiatives for Tenants (SNAP) |  |  |
| - ENERGY and MOH | - Explore ways to provide direct assistance to tenants that are not sub-metered and do not directly benefit under the existing and proposed rate mitigation programs Considerations - MHO leading any legislative/regulatory changes needed to have tenants benefit from program. Consider whether benefits are limited to 8% and GA (rather than OESP which is harder to provide to tenants who do not pay their bills). - ENERGY working with MCSS to streamline/automate enrollment for ODSP/OW consumers into OESP. | - Report back to TBC/MBC and Cabinet in spring 2017 (Per Cabinet Minute) |
| - Stakeholder/Agency Outreach (Communications) |  |  |
| - ENERGY | - Minister’s letters to: - Ratepayers; - LDCs; - Business (e.g., OCC, CME, Concerned Manufactures, etc); and - Agencies (i.e., IESO, OPG, OEB and H1) | - Early-mid March |
| - FAO Engagement |  |  |
| - ENERGY, MOF/OFA, FAO | - Provide FAO staff with a technical briefing on the OFHP | - March 9, 2017: Preliminary discussion. |