Action Items – April 20, 2017

GA Refinancing

- LSB / Blakes to turn around revised document today with comments due by end of day Sunday

- IESO / OPG to work together on outstanding issue regarding OPG cash flows

- OPG to draft terms of guarantee  to dealers which will be presented to dealers

- MOF (IGS) to work through equity injection mechanics and will report back next week

- IESO to work with KPMG on IESO recovery mechanism

- Pens down on refinancing legislation April 28

Other OFHP Initiatives

- Pens down on social program legislation April 28

- ENERGY working with MCSS on automatic enrolment

- ENERGY meeting with COO next week on FN rate

- ENERGY / MOF / OEB / ICF discussions with CRA ongoing on wet signature

- Affordability Fund advisory committee met this week and reached consensus on three LDCs + two social agencies to be represented on Trust Board (Ottawa Carlton UW / Advocacy Centre for Tenants Ontario / Thunder Bay Hydro / Hydro One / Alectra)

- ENERGY continues to work with OCC / CME on targeted outreach regarding energy programs for business, including ICI

Other Items

- ENERGY drafting TB / LRC submissions as well as presentation to Cabinet – May 9, 10