Action Items – April 25, 2017

- Global Adjustment

    - LSB / Blakes turning around comments received over the weekend; new draft of the legislation will be circulated later today or early tomorrow

    - Comments on next draft of legislation will be due Wednesday to keep on track with Friday pens down on legislation

    - E&Y opinion on track

    - OPG undertaking modelling but initial borrowing amount will come from formula in legislation

    - Ministry working with Navigant on report (interim report expected in a couple of weeks followed by a final report)

    - CoS to discuss inflation provision with PO to confirm comfort with including it in regulation vs legislation

    - IESO working with KPMG on opinion (draft tracking for later this week)

    - IESO to discuss Board assurances with Ministry later this week

    - OEB continues to work through a few issues with LSB (e.g. role in review of admin costs, timing of revised RPP, why there needs to be an OEB objective)

    - MOF and ENERGY Ministers will be signatories to springing guarantee, performance guarantee and protection to boards

- Other OFHP Items

  - RRRP, OESP, FN

    - New turn of social legislation expected today for comment by Wednesday to meet Friday pens down timeline

    - Ministry sorting through issue with Dubreuilville to ensure the legislation is permissive enough to allow them to be eligible

    - Ministry meeting with COO tomorrow on FN rate implementation

    - Ministry to meet with MCSS re: taking over OESP administration

  - Affordability Fund

    - Hydro One to prepare letters that will go out to social service agencies

  - ICI

    - Ministry continues to work with CME / OCC on targeted outreach

- Other Items

  - IGS continues to work with MOF / TBS on equity injection to ensure we have appropriate approvals for appropriation room this fiscal year, needs to be included in Estimates so approvals required on Thursday

  - OFA working with TD on content to be included in TB submission on financial viability

  - MO to work with MOF / TBS MOs to request their Ministers for debate on May 15th and 16th