
Ontario’s Fair Hydro Plan – Critical Path Dates
(Week of May 15, 2017)

· April 28, 2017 – Pens down on drafting the Legislation  

· May 1, 2017 – KPMG and E&Y Opinions 

· May 2, 2017 – Caucus Briefing  

· May 3, 2017 
· Fiscal Prep Briefing
· MMP Briefing 


· May 8, 2017 – Interim Report from Navigant (Final report due June 5, 2017) 

· May 9, 2017 – TB/MBC Report Back
· Accounting 
· Financial viability work (OFA in collaboration with TD Securities)
· Legal considerations
· OPG Business Plan Concurrence – Required for OEB process

· May 10, 2017 – LRC/Cabinet on Legislation  

· May 11, 2017 – Introduction Legislation 

· May 12, 2017 – Regulatory Posting

· May 15, 2017 – Opposition Briefings

· May 2017 –  Agency Admin items 
· OPG Shareholder Resolution
· Indemnities for OPG and IESO Boards 
· s.28 Approval

· [bookmark: _GoBack]Week of May 15, 2017 – House debate on Legislation 

· Week of May 24, 2017  – Committee to review Legislation (TBD)
· Public Hearings 

· Week of May 29, 2017 
· Committee / Clause by Clause / Amendments  
· Passage (TBD) 

· June 14 and 27, 2017 – Regulations (Direct to Cabinet) 



