Ontario’s Fair Hydro Plan – Critical Path Dates

(Week of May 15, 2017)

- April 28, 2017 – Pens down on drafting the Legislation

- May 1, 2017 – KPMG and E&Y Opinions

- May 2, 2017 – Caucus Briefing

- May 3, 2017

  - Fiscal Prep Briefing

  - MMP Briefing

- May 8, 2017 – Interim Report from Navigant (Final report due June 5, 2017)

- May 9, 2017 – TB/MBC Report Back

  - Accounting

  - Financial viability work (OFA in collaboration with TD Securities)

  - Legal considerations

  - OPG Business Plan Concurrence – Required for OEB process

- May 10, 2017 – LRC/Cabinet on Legislation

- May 11, 2017 – Introduction Legislation

- May 12, 2017 – Regulatory Posting

- May 15, 2017 – Opposition Briefings

- May 2017 –  Agency Admin items

  - OPG Shareholder Resolution

  - Indemnities for OPG and IESO Boards

  - s.28 Approval

- Week of May 15, 2017 – House debate on Legislation

- Week of May 24, 2017  – Committee to review Legislation (TBD)

- Public Hearings

- Week of May 29, 2017

- Committee / Clause by Clause / Amendments

- Passage (TBD)

- June 14 and 27, 2017 – Regulations (Direct to Cabinet)