Action Items – June 8

- GA Refinancing

  - Ministry tracking 8 regs for next week

  - Ministry moved OESP reg to June 27

    - Ministry continues to work with MCSS on OESP automatic enrolment, which is tracking for Sept at the earliest

  - Ministry continues to work on general reg and requires input from OPG, IESO and OEB to ensure they have what they need

  - TBS would like a road map to facilitate the presentation at TB

  - OPG to provide language to Ministry for regulation drafting

  - OPG to draft a deck for Minister’s OFHP implementation briefing with input from IGSs

  - IESO expecting AG coming to their Board on June 14

  - IESO is working with KPMG to review the interest cost coming back to IESO from OPG during moratorium period

  - OEB drafting supplementary report to go out with revised pricing on June 22

    - OEB to consider announcing pricing earlier in the day rather than afternoon

  - OEB refining answer and key messages to how HydroOne rate application impacts OFHP and will share with Ministry

  - Ministry/OFA to provide comments back to OPG on Provincial Support Agreement Term Sheet by next week

  - MOF, not TBS, to provide S. 28 approval

  - OPG/IESO to confirm timing of when they need Board indemnities (potentially required before IESO Board meeting on the 14th of June)

  - MOF/TBS to look into whether appropriation from TB is required to facilitate the S.28 approval

  - Ministry reviewing CEB/DRC comparison document and will provide comments next week.

- Other OFHP Initiatives

  - RRRP, OESP and FN:

    - Ministry working with Chiefs on First Nations Delivery credit with Chiefs expecting to table and pass a resolution next week on who receives credit

  - Affordability Fund:

    - Formal written invitation  being sent to  final trustee who has agreed verbally