Outstanding Business Issues – Ontario Fair Hydro Plan

| Issue | Overview | Supporting Documentation | Next Steps |
| --- | --- | --- | --- |
| Guarantees | - Province to provide contingent supports to enable structure | - Draft Term Sheet - Performance Guarantee - Service Guarantee | - OPG/MOF/ENE to discuss respective comments on the term sheet - ENE/MOF tracking to TB in September for approval Timing: Sept 26 TB/MBC |
| Equity Injection | - Province to purchase shares of OPG on a monthly basis | - Master Subscription Agreement - Service Level Agreement - Notice of Subscription - Amendment to Articles | - OFA / Energy to determine required monthly process and sign-off mechanism Timing: Late Sept/Early Oct |
| PILs Exemption | - Province to mitigate cost to ratepayers by minimizing PILs payable by OPG financing vehicle | - Tax Regulation | - MOF legal to draft comfort letter and regulation Timing: Regulation by fall |
| Subordinated Debt Loan Agreement | - OPG will lend the equity injection from the Province to the Trust by way of subordinated debt | - Draft Term Sheet - Debt Loan Arrangement | - OFA to provide comments - OPG to draft Debt Loan Arrangement Timing: Late Sept |
| OEB Rate & Fees | - OPG is allowed to charge a management fee for its services made up of 1)base fee and 2) performance fee | - Draft Base Fee framework - Draft Performance Fee framework - Regulation | - OPG, ENE and OFA to determine role of OEB in determining fees OPG charges Timing: Regulation by the fall |