Ontario’s Fair Hydro Plan – Critical Path Dates

(Week of May 1, 2017)

- April 28, 2017 – Pens down on drafting the Legislation

- May 1, 2017 – KPMG and E&Y Opinions

- May 2, 2017 – Caucus Briefing

- May 3, 2017 – Fiscal Prep Briefing

- May 2017 – MMP Briefing (TBD)

- May 2017 –  Agency Admin items (TBD)

  - OPG Shareholder Resolution

  - Indemnities for OPG and IESO Boards

- May 8, 2017 – Interim Report from Navigant (Final report due June 5, 2017)

- May 9, 2017 – TB/MBC Report Back

  - Legal Opinions

  - Accounting Opinion

  - OFA Financial Viability work (in collaboration with TD Bank)

  - OPG Business Plan Concurrence – Required for OEB process

- May 10, 2017 – LRC/Cabinet on Legislation

- May 11, 2017 – Introduction Legislation

- May 2017 – Regulatory Posting (TBD)

- May 2017 – Opposition Briefings (TBD)

- May 15, 16, 17, and 18, 2017 – House debate on Legislation (TBD)

- Week of May 24, 2017  – Committee to review Legislation (TBD)

- Public Hearings

- Week of May 29, 2017

- Clause by Clause / Amendments

- Passage (TBD)

- June 2017 – LRC with Regulations