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· April 28, 2017 – Pens down on drafting the Legislation  

· May 1, 2017 – KPMG and E&Y Opinions 

· May 2, 2017 – Caucus Briefing  

· May 3, 2017 – Fiscal Prep Briefing

· May 2017 – MMP Briefing (TBD)

· May 2017 –  Agency Admin items (TBD)
· OPG Shareholder Resolution
· Indemnities for OPG and IESO Boards

· May 8, 2017 – Interim Report from Navigant (Final report due June 5, 2017) 

· May 9, 2017 – TB/MBC Report Back
· Legal Opinions
· Accounting Opinion
· OFA Financial Viability work (in collaboration with TD Bank)
· OPG Business Plan Concurrence – Required for OEB process

· May 10, 2017 – LRC/Cabinet on Legislation  

· May 11, 2017 – Introduction Legislation 

· May 2017 – Regulatory Posting (TBD)

· May 2017 – Opposition Briefings (TBD)

· May 15, 16, 17, and 18, 2017 – House debate on Legislation (TBD)

· Week of May 24, 2017  – Committee to review Legislation (TBD)
· Public Hearings 

· Week of May 29, 2017 
· Clause by Clause / Amendments  
· Passage (TBD) 

· June 2017 – LRC with Regulations  



