## Sheet1
Required For
Issue | Status | Deliverable | Due Date | Rating Agency | OPG Board Approval | Comment
Approval
Fair Allocation Curve | Draft Letter to be provided to OPG by Sept 15 | Confimation Letter from Minister for 2 yr Re-adjusment amount | 2017-09-18 | X | X
| OPG & MOE to have joint model review Sept 15 | Confirmation Letter from DM/ADM for Full allocation curve for the duration of the Program inlcuding the re-adjustment amount | 2017-09-20 | X | X
Provincial Support Agreement | Revised Draft term Sheet to be circulated today | Final Term Sheet | 2017-09-15 |  | X | E&Y confirmation required prior to Board approval
|  | Draft Agreement | 2017-09-20 | X | X
Regulation relating to Fees & OEB involvement | MOE circulated to OEB for comment | Draft Regulation | 2017-09-25 |  | X | E&Y confirmation required prior to Board approval
LDC Commingling Risk | IESO to provide LC as required | Draft MTSA | 2017-09-25 | X
Interest payment during Moratorium Period | MOE & IESO to discuss required Reg Amendments | Tern Sheet - Required Changes to Regulations | 2017-09-20 | X | X
| Torys to provide Structural Input | Draft Regulation | 2017-09-29 | X
Share Purchase Agreement | Waiting for confirmation /comments from MOE/MOF | Finalized Master Share Subscription Agreement | 2017-09-25 |  | X
including concurrence with equity forecast requirement and approvals process